## Summary
CanDoItAll canonical architecture review bundle v2
Updated for CRM/HR module and node-as-carrier architecture stance.
Metric | Value | Type
Review date | 2026-04-04 | Static input
Repository | CanDoItAll-crm-hr-module | Static input
Baseline snapshot | CanDoItAll-canvas-drawing-refactor | Static input
Previous bundle | candoitall-canonical-architecture-review-bundle | Static input
Skillset | candoitall-codex-architecture-review-skillset | Static input
Findings count | 15 | Derived
Critical findings | 3 | Derived
High findings | 10 | Derived
Current overall score (%) | 32 | Derived
Projected post-remediation score (%) | 78 | Derived
dotnet runtime in container | BLOCKED | Caution
Key decision | Node stays the stable universal carrier for workbench-authored thinking. | Control
Key warning | Do not keep party truth duplicated across metadata, assignment rows, and module-local fields. | Caution

## Findings
Findings
15 findings including CRM/HR-specific canonical-model issues.
ID | Severity | Skill Source | Category | Title | Problem Summary | Evidence | Root Cause | Remediation Goal | Stabilize When | Validation Strategy | Prospective Recheck Result | QA Status | Phase | Subbundle Path | Dependencies / Notes
ACR-005 | Critical | feature-block-architecture-review | Invariant drift | Workbench reparent flow lacks explicit cycle and parent invariants | Projects module rejects hierarchy cycles, but workbench reparent flow updates parent/link data without a visible equivalent invariant guard for node graph cycles or self-parenting. | src/CanDoItAll.Modules.Projects/ProjectModels.cs:748-795 ValidateHierarchyConnectionAsync rejects self-parent and descendant cycles for project hierarchy src/CanDoItAll.Modules.Workbench/ProjectWorkbenchModels.cs:598-643 ReparentObjectAsync mutates parent/link state without visible cycle validation src/CanDoItAll.Modules.Workbench/ProjectWorkbenchModels.cs:1949-1952 NormalizeEditableParentNodeKey only normalizes null/whitespace | Invariant logic exists in one canonical area but was not promoted into a shared structure mutation policy for workbench node reparenting. | Centralize graph mutation invariants in ProjectStructureInvariantService and enforce them on create/reparent/link/move operations with dedicated tests. | Now | Add failing tests for self-parent, descendant-parent, cross-project edge violations, and illegal kind-to-kind relations before refactor; make them green through one invariant service. | Prospective pass if every mutation entry point routes through the invariant service and tests cover cycle cases. | Pass | Phase 0 | subbundles/ACR-005-workbench-reparent-flow-lacks-explicit-cycle-and-parent-invariants | Depends on ACR-011. Interacts with ACR-003 and ACR-004.
ACR-011 | High | canonical-model-review | Testability drift | Core canonical-invariant and projection-equivalence tests are missing | The repo has meaningful tests, but it lacks a dedicated ring that protects truth ownership, relation invariants, node-kind registry behavior, node-assignment integrity, node-evolution history, and multi-projection equivalence during architectural stabilization. | tests/CanDoItAll.Tests.Integration/ProjectWorkbenchServiceIntegrationTests.cs contains workbench mutation/projection tests, but no visible reparent-cycle rejection coverage tests/CanDoItAll.Tests.Integration/ProjectPartyAssignmentIntegrationTests.cs:23-66 covers positive project/node assignment persistence, but not orphan node keys, mismatched projects, or illegal node-kind roles tests/CanDoItAll.Tests.Components/CrossModuleResponsiblePartyPageTests.cs:29-53 and 68-116 cover positive round-trips, but not ownership divergence or canonical-source enforcement | Existing tests grew around current behavior, not around the future canonical contracts now needed for stabilization work. | Create an architectural test ring for invariants, relation policy, assembled graph equivalence, cache non-authoritativeness, node-assignment integrity, and node-evolution history. | Now | Add failing characterization and invariant tests before refactor; keep them green throughout each phase. | Prospective pass if each remediation phase lands with new guardrail tests before broad refactors. | Pass | Phase 0 | subbundles/ACR-011-core-canonical-invariant-and-projection-equivalence-tests-are-missing | Foundational for every other finding.
ACR-013 | High | feature-block-architecture-review | Invariant drift | Node-scoped CRM/HR assignments use a soft NodeKey reference without canonical integrity checks | ProjectPartyAssignment stores NodeKey as a plain string and SaveAssignmentAsync validates only project and party existence. There is no visible check that the referenced node exists, belongs to the same project, or allows the requested role. | src/CanDoItAll.Modules.CrmHr/CrmHrBusinessModels.cs:413-427 ProjectPartyAssignment stores NodeKey as a string src/CanDoItAll.Modules.CrmHr/CrmHrBusinessModels.cs:668-683 configuration indexes NodeKey but does not enforce canonical node integrity src/CanDoItAll.Modules.CrmHr/CrmHrServices.cs:4421-4500 SaveAssignmentAsync validates project/party, then upserts by ProjectId/PartyId/AssignmentKind/NodeKey without validating node existence or kind policy tests/CanDoItAll.Tests.Integration/ProjectPartyAssignmentIntegrationTests.cs:40-48 uses an arbitrary node key string ('work-item-alpha') as a valid node-scoped assignment input | The generic project-party bridge was built before a canonical node reference validator and actor-role policy existed. | Validate node-scoped assignments against the canonical graph or node carrier before persistence; reject orphan node keys, mismatched project scope, and illegal role-kind combinations. Consider a stronger target reference over time. | Now | Add failing tests for orphan node keys, wrong-project node keys, and disallowed node-kind role assignments before refactor; make them green via one validator. | Prospective pass if node-scoped assignments cannot be saved unless the target node exists in the same project and the role is allowed for that node kind. | Pass | Phase 0 | subbundles/ACR-013-node-scoped-crm-hr-assignments-use-a-soft-nodekey-reference-without-cano | Depends on ACR-011. Full role validation depends on ACR-003; minimal existence/project validation can start immediately.
ACR-012 | Critical | canonical-model-review | Source-of-truth drift | Party responsibility truth is duplicated across node metadata, assignment tables, and module-local fields | CRM/HR responsibility is now stored in more than one editable place. Participant, meeting, and work-item flows write both node metadata and project-party assignments, while Resources, Validation, and TestLab also store module-local responsible-party fields. | src/CanDoItAll.Modules.Workbench/Pages/ProjectStructurePage.PartyIntegration.cs:250-257, 293-305, 330-351, 370-405 save both metadata and ProjectPartyAssignment rows src/CanDoItAll.Modules.Workbench/ProjectWorkbenchMetadata.cs:296-299 and 331-334 store LinkedPartyId / AssigneePartyId inside node metadata src/CanDoItAll.Modules.Resources/ResourceModels.cs:84-92 stores OwnerPartyId / MaintainerPartyId src/CanDoItAll.Modules.Validation/ValidationModels.cs:50-58 stores ResponsiblePartyId src/CanDoItAll.Modules.TestLab/TestLabModels.cs:18-25 stores ResponsiblePartyId | CRM/HR integration added reusable party semantics without first establishing one canonical actor-assignment owner across node-scoped and module-scoped responsibility. | Choose one canonical owner for cross-cutting actor responsibility. Recommended direction: canonical ActorAssignment model with explicit scopes; node metadata keeps only display/cache data if needed, and module-local fields become derived mirrors or migrate later. | Now | Add tests proving there is only one writable source for node-scoped responsibility, and verify that module-level mirrors do not drift from the canonical assignment owner. | Prospective pass if participant/meeting/work-item party edits change one canonical assignment owner and any metadata/module-local display fields are derived or mirrored one-way only. | Pass with caution | Phase 1 | subbundles/ACR-012-party-responsibility-truth-is-duplicated-across-node-metadata-assignment | Depends on ACR-003 and ACR-011. Enables ACR-013 and ACR-015. Strongly coupled with ACR-014.
ACR-003 | High | canonical-model-review | Naming / concept drift | Type and subtype semantics are weak and partly owned by the UI catalog | ProjectObjectType is broad, subtypes are strings, metadata validation is shallow, and the canvas catalog carries substantial semantic truth about participants, work items, decisions, and other node kinds. CRM/HR role semantics are partly inferred from subtype strings rather than a canonical registry. | src/CanDoItAll.SharedKernel/ProjectObjectContracts.cs:3-44 broad enums exist but no canonical kind registry src/CanDoItAll.Modules.Workbench/ProjectStructureCanvasCatalog.cs:6-28 and ProjectStructureCanvasCatalog.RichDefinitions.cs:132-144 UI create definitions encode semantic defaults and field sets src/CanDoItAll.Modules.Workbench/ProjectWorkbenchMetadata.cs:625-660 metadata validation only checks broad family/type alignment src/CanDoItAll.Modules.Workbench/Pages/ProjectStructurePage.PartyIntegration.cs:466-474 participant role is inferred from subtype strings | Type semantics grew through UI creation and metadata family needs instead of a central domain registry. | Introduce a canonical NodeKindRegistry that defines allowed facets, transitions, relation policy, actor role policy, time semantics, execution semantics, and UI descriptors from one place. | Now | Registry tests; one semantic source for UI/MCP/import/compiler classification; smoke tests that UI catalogs are generated from registry definitions. | Prospective pass if all type/subtype decisions flow through registry lookups and the UI becomes a consumer, not the semantic owner, of node kinds. | Pass | Phase 1 | subbundles/ACR-003-type-and-subtype-semantics-are-weak-and-partly-owned-by-the-ui-catalog | Foundational for ACR-001, ACR-002, ACR-004, ACR-005, ACR-012, ACR-013, and ACR-014.
ACR-004 | High | canonical-model-review | Boundary drift | Relation semantics are blurred and hierarchy is stored twice | ParentNodeKey and hierarchy link rows both describe parentage, while dependency analysis folds ancestry into prerequisites and inverse blocking semantics. As CRM/HR links and critical-path logic grow, blurred graph semantics become more dangerous. | src/CanDoItAll.Modules.Workbench/ProjectWorkbenchModels.cs:441-502 CreateObjectAsync writes ParentNodeKey and UpsertLinkAsync src/CanDoItAll.Modules.Workbench/ProjectWorkbenchModels.cs:598-643 ReparentObjectAsync updates ParentNodeKey and recreates link rows src/CanDoItAll.Modules.Workbench/ProjectWorkbenchModels.cs:1990-1993 ResolveHierarchyLinkKind maps hierarchy through generic link kinds src/CanDoItAll.Modules.Workbench/ProjectStructureDependencyAnalysis.cs:81-125 prerequisites include ancestors, explicit DependsOn, and inverse Blocks | Tree placement, dependency edges, and execution semantics evolved together without a strict relation taxonomy and one canonical hierarchy owner. | Choose one canonical hierarchy owner for workbench-authored nodes, model dependency/association edges explicitly, and define a relation policy matrix by node kind. | Now | Relation invariant tests, graph cycle tests, and projection tests proving hierarchy and dependency semantics remain distinct. | Prospective pass if hierarchy, dependency, and association edges have separate canonical meanings and storage owners. | Pass | Phase 1 | subbundles/ACR-004-relation-semantics-are-blurred-and-hierarchy-is-stored-twice | Foundational for ACR-001, ACR-002, ACR-005, ACR-006, and ACR-014.
ACR-001 | Critical | canonical-model-review | Source-of-truth drift | Persisted system-managed workbench graph acts as a parallel truth | ProjectWorkbenchService still synchronizes Projects, Resources, Factory, Validation, and TestLab canonical entities into persisted ProjectObjectRecord / ProjectObjectLinkRecord rows, and structure/calendar/Gantt reads still flow through that synced copy. The new CRM/HR overlays would now stack on top of a graph that is already a parallel truth. | src/CanDoItAll.Modules.Workbench/ProjectWorkbenchModels.cs:348-438 structure and calendar reads call SyncGraphAsync before reading workbench records src/CanDoItAll.Modules.Workbench/ProjectWorkbenchModels.cs:1666-1943 SyncGraphAsync assembles expected nodes/links from Project, ProjectPhase, ProjectResource, PromptRun, PromptRunNode, ValidationRun, TestPlan, and ProjectHierarchyLink and persists them src/CanDoItAll.Modules.Workbench/ProjectGanttPreviewService.cs:10-17 Gantt preview is built from workbench structure output | A convenience projection cache gradually became the effective read model and therefore a second authoritative graph. | Introduce one assembled canonical graph for reads and projections, built from upstream canonical owners + workbench-owned custom nodes + canonical actor assignments/facets. If a persisted cache remains, mark it explicitly non-authoritative. | Now | Add assembled-graph equivalence tests for structure/calendar/Gantt and actor overlays; prove any retained cache rebuild is lossless; verify system-managed rows are no longer authoritative. | Prospective pass if structure/calendar/Gantt consume CanonicalGraphAssembler output instead of persisted synced rows and actor overlays are attached during graph assembly, not by mutating the synced copy. | Pass with caution | Phase 2 | subbundles/ACR-001-persisted-system-managed-workbench-graph-acts-as-a-parallel-truth | Depends on ACR-003, ACR-004, ACR-011, and the actor-assignment ownership work in ACR-012/ACR-013. Strongly coupled with ACR-006 and ACR-009.
ACR-006 | High | canonical-model-review | Projection drift | Calendar and Gantt are projections over a persisted projection | Calendar and Gantt do not build directly from canonical owners; they depend on workbench structure output that itself depends on SyncGraphAsync. CRM/HR-linked scheduling and ownership overlays would therefore be computed over a projection chain rather than one graph truth. | src/CanDoItAll.Modules.Workbench/ProjectWorkbenchModels.cs:396-438 calendar read path depends on SyncGraphAsync and workbench records src/CanDoItAll.Modules.Workbench/ProjectGanttPreviewService.cs:10-17 Gantt preview uses workbench structure src/CanDoItAll.Modules.Workbench/ProjectWorkbenchModels.cs:2552-2590 structure node mapping mixes metadata, signals, routes, storage, and schedule info | Convenient reuse of one persisted structure DTO turned projections into chained read models. | Create separate structure, calendar, timeline/Gantt, and summary builders that consume one assembled canonical graph plus explicit workbench overlays. | Before next feature wave | Projection-equivalence tests, golden files for Gantt/Calendar, and proof that projection builders are side-effect free. | Prospective pass if builders read from the same assembled graph and no projection becomes a write model. | Pass with caution | Phase 2 | subbundles/ACR-006-calendar-and-gantt-are-projections-over-a-persisted-projection | Depends on ACR-001, ACR-003, ACR-004, and ACR-011.
ACR-014 | High | feature-block-architecture-review | Lifecycle drift | Node reclassification and typed lifecycle history are insufficient for note→task/decision evolution | The product workflow starts with fast brainstorming notes that later become structured tasks, decisions, or other typed nodes. Current reclassification mutates the same row in place, only supports note→block / block→block, and does not preserve typed transition history. | src/CanDoItAll.Modules.Workbench/ProjectWorkbenchModels.cs:896-927 ReclassifyObjectAsync mutates the same ProjectObjectRecord in place src/CanDoItAll.Modules.Workbench/ProjectWorkbenchModels.cs:2352-2358 IsSupportedReclassification only allows ProjectBlock->ProjectBlock and Note->ProjectBlock src/CanDoItAll.Modules.Workbench/Pages/ProjectStructurePage.NodeMutations.cs:12-17 and 107-125 UI currently exposes note→block and block-type change only User clarification captured in inputs/02-user-clarifications.md: the core workflow is brainstorming via simple nodes that later become richer typed blocks/tasks/decisions, and preserving that reasoning history matters | Node lifecycle was modeled as a simple type mutation rather than a first-class transition/facet history over a stable node carrier. | Keep node identity stable, preserve brainstorming history, and model typed evolution through facet activation/invalidation or node-kind transition history rather than destructive in-place mutation. | Before next feature wave | Add transition tests for note→task, note→decision, and note→block; verify history survives; verify assignments and spatial semantics are preserved or transformed by policy. | Prospective pass if a brainstorm node can evolve into a task/decision/block without losing node identity, rationale history, or semantically meaningful position/marker context. | Pass with caution | Phase 2 | subbundles/ACR-014-node-reclassification-and-typed-lifecycle-history-are-insufficient-for-n | Depends on ACR-003, ACR-008, ACR-011, and should coordinate with ACR-012.
ACR-002 | High | canonical-model-review | Boundary drift | ProjectObjectRecord is an overloaded universal box | One record mixes node carrier truth, spatial semantics, schedule, markers, route, artifact binding, storage/media references, and metadata-driven subtype payloads. With CRM/HR, the same box also becomes the anchor for party assignment metadata. | src/CanDoItAll.Modules.Workbench/ProjectWorkbenchModels.cs:26-60 ProjectObjectRecord contains domain, spatial, schedule, storage, route, and signal fields in one type src/CanDoItAll.Modules.Workbench/ProjectWorkbenchModels.cs:143-176 ProjectStructureNode exposes many mixed concerns from one source record src/CanDoItAll.Modules.Workbench/ProjectWorkbenchMetadata.cs:165-190 metadata envelope packs multiple optional families src/CanDoItAll.Modules.Workbench/Pages/ProjectStructurePage.PartyIntegration.cs:240-406 party integration writes CRM/HR-linked metadata back into the same node payload | Fast feature waves were absorbed by one universal node record instead of stable companion concepts and typed facets. | Keep Node as the stable workbench-authored carrier, but split schedule, spatial-semantic state, signals, attachment/storage bindings, and typed facet data into clearly owned companion records or facet tables. | Before next feature wave | Migration tests for the record split, serialization round-trips, and mutation tests proving each concern is edited through the correct owner. | Prospective pass if a stable NodeCarrier remains, semantically meaningful X/Y and marker sets stay canonical, and extension/facet data moves out of the universal box. | Pass with caution | Phase 3 | subbundles/ACR-002-projectobjectrecord-is-an-overloaded-universal-box | Depends on ACR-003 and ACR-004. Informs ACR-008 and ACR-014. Simplifies ACR-009.
ACR-008 | High | canonical-model-review | Boundary drift | Spatial semantics are canonical, but marker ownership is duplicated and under-modeled | X/Y position and semantic markers are clearly important to the product, but marker state is still written through both dedicated columns and metadata. The model also needs a sharper split between canonical spatial-semantic state and ephemeral canvas UI state. | src/CanDoItAll.Modules.Workbench/ProjectWorkbenchModels.cs:52-53 ProjectObjectRecord stores PositionX / PositionY src/CanDoItAll.Modules.Workbench/ProjectWorkbenchModels.cs:143-176 ProjectStructureNode exposes X, Y, legacy marker columns, and marker collections together src/CanDoItAll.Modules.Workbench/ProjectWorkbenchMetadata.cs:557-616 metadata serializer resolves marker sets and primary marker src/CanDoItAll.Modules.Workbench/ProjectWorkbenchModels.cs:1399-1404 ApplyPrimaryMarker writes legacy marker columns from the marker set src/CanDoItAll.Modules.Workbench/ProjectWorkbenchModels.cs:113-130 ProjectWorkbenchViewStateRecord keeps separate viewport/state JSON, showing that some UI state is already distinct | The system correctly kept spatial data near nodes, but signal semantics and view semantics never received a dedicated canonical model boundary. | Model spatial semantics explicitly as canonical node-owned data (carrier or spatial facet), keep semantic marker sets as the single writable owner, and keep viewport/selection/expanded state in view-state persistence only. | Later in current stabilization wave | Signal/spatial mutation tests and migration assertions proving marker edits round-trip through one owner while view-state remains separate. | Prospective pass if semantic X/Y and markers remain canonical, but only one writable marker owner exists and ephemeral canvas state stays in view-state records. | Pass with caution | Phase 3 | subbundles/ACR-008-spatial-semantics-are-canonical-but-marker-ownership-is-duplicated-and-u | Depends on ACR-002 and should inform ACR-014 because typed evolution must preserve spatial semantics.
ACR-015 | High | canonical-model-review | Boundary drift | Cross-module responsibility model is fragmented and lacks one canonical actor-assignment owner | Resources, Validation, TestLab, project-party assignments, and workbench node metadata each represent responsibility in their own way. There is no explicit ownership matrix for who owns project-level, node-level, and module-level actor assignments. | src/CanDoItAll.Modules.Projects/ProjectPartyIntegrationContracts.cs:62-119 defines a generic project-party assignment contract with optional NodeKey src/CanDoItAll.Modules.CrmHr/CrmHrBusinessModels.cs:413-427 defines ProjectPartyAssignment with project-, opportunity-, phase-, and node-scoped fields src/CanDoItAll.Modules.Resources/ResourceModels.cs:84-92, src/CanDoItAll.Modules.Validation/ValidationModels.cs:50-58, and src/CanDoItAll.Modules.TestLab/TestLabModels.cs:18-25 store responsibility directly inside module aggregates tests/CanDoItAll.Tests.Integration/CrmHrCrossModuleIntegrationTests.cs:186-255 demonstrate positive round-trip behavior across these modules, but not a canonical ownership rule | CRM/HR integration correctly broadened project actor semantics, but did so via multiple local representations before one cross-module actor-assignment model was fixed. | Define one canonical ActorAssignment model plus an ownership matrix for project-, node-, and module-scoped responsibility. Module-local fields either become derived mirrors or remain authoritative only until their migration phase is complete. | Before next feature wave | Add canonical-ownership tests and migration tests proving which layer owns each responsibility fact and how mirrors stay consistent. | Prospective pass if every responsibility fact can answer one question clearly: who owns it canonically, who only mirrors it, and who only projects it? | Pass with caution | Phase 3 | subbundles/ACR-015-cross-module-responsibility-model-is-fragmented-and-lacks-one-canonical | Depends on ACR-012 and ACR-013. Influenced by ACR-003 and ACR-014.
ACR-007 | Medium | canonical-model-review | Integration drift | Route, artifact binding, and storage/media concerns leak into node truth | Route strings are rewritten during project moves and storage/media references live inside the main node record, making navigation and attachment concerns look canonical even though they are transport/integration concerns. | src/CanDoItAll.Modules.Workbench/ProjectWorkbenchModels.cs:1005-1013 MoveDescendantsToProjectAsync rewrites Route src/CanDoItAll.Modules.Workbench/ProjectWorkbenchModels.cs:26-60 ProjectObjectRecord includes route and file/media references src/CanDoItAll.Modules.Workbench/ProjectWorkbenchModels.cs:2552-2590 structure mapping exposes route/storage concerns directly | Convenient transport/navigation fields were stored with node truth instead of separate attachment/navigation models. | Create typed artifact bindings and attachment/media models; compute routes through resolvers instead of persisting them as canonical node truth. | Later in current stabilization wave | Attachment binding tests, route resolver tests, and project move tests proving routes are recomputed rather than rewritten as canonical data. | Prospective pass if route becomes derived and attachment bindings are explicitly typed. | Pass | Phase 3 | subbundles/ACR-007-route-artifact-binding-and-storage-media-concerns-leak-into-node-truth | Easier after ACR-002 and ACR-014 define the node/facet seam.
ACR-009 | High | architecture-drift-audit | Dependency drift | ProjectWorkbenchService is an oversized orchestration hotspot | A 2900+ line service owns graph sync, CRUD, transfer, media save, view state, command translation, DTO mapping, and now indirectly participates in party integration flows, making safe change difficult. | src/CanDoItAll.Modules.Workbench/ProjectWorkbenchModels.cs:314-2931 ProjectWorkbenchService spans graph sync, mutations, view state, mapping, and helper logic src/CanDoItAll.Modules.Workbench/Pages/ProjectStructurePage.PartyIntegration.cs depends on ProjectWorkbenchService + ProjectPartyIntegrationBridge for one cohesive workflow inventory: Modules.Workbench is referenced by Web, Composition, MCP.ProjectStructure, Tests.Support, Tests.Unit, Tests.Components, and CRM/HR-adjacent pages | Wave-by-wave growth concentrated orchestration into one central service rather than layered collaborators. | Split graph assembly, mutation invariants, projection builders, attachment/media handling, typed-facet lifecycle, and view-state handling into focused services behind a thin façade. | Before next feature wave | Characterization tests around façade behavior, constructor dependency shrinkage, and targeted tests for extracted collaborators. | Prospective pass if the service reduces to orchestration over smaller collaborators and no collaborator mixes unrelated roles. | Pass with caution | Phase 4 | subbundles/ACR-009-projectworkbenchservice-is-an-oversized-orchestration-hotspot | Execute after the semantic seams from ACR-001/002/003/004/012/014 exist; avoid cosmetic extraction first.
ACR-010 | Medium | architecture-drift-audit | Runtime / operational drift | Lease scope granularity does not match mutation granularity | Scope kinds include ProjectNode, but many agent mutation flows still take project-wide leases, which may over-serialize work and obscure future permission boundaries. | src/CanDoItAll.Modules.Workbench/ProjectStructureAgentContracts.cs:26-74 defines Project and ProjectNode lease scopes src/CanDoItAll.Modules.Workbench/ProjectStructureLeaseService.cs:197-222 project-scoped acquisition helper still dominates current flow Previous bundle and current static scan did not find a broad rollout of node-level scope selection in mutation entry points | The runtime safety model was introduced conservatively before mutation invariants and canonical ownership were stable enough for finer-grained locks. | Define a mutation-to-scope policy matrix and progressively move safe node-level mutations to narrower scopes with telemetry and tests. | Later | Concurrency tests, lease contention telemetry, and authorization tests for node/project/repo-branch scope selection. | Prospective pass if scope selection aligns with mutation semantics and remains conservative where invariants require broader locks. | Pass | Phase 4 | subbundles/ACR-010-lease-scope-granularity-does-not-match-mutation-granularity | Defer until ACR-005 and ACR-011 are implemented and the graph mutation rules are stable.

## CanonicalConcepts
Canonical concepts
Current and target ownership of the most important concepts.
Concept | Current Primary Kind | Current Owner | Current Problem | Target Kind | Target Owner
Workbench-authored node carrier | Mixed-role canonical-ish entity | ProjectObjectRecord in Workbench | Owns identity, text, route, storage/media, marker legacy columns, XY, schedule, metadata envelope, and parent key all at once. | Canonical entity + typed facets | NodeCarrier + companion facet records in Workbench
Node kind semantics | Split semantics | ProjectObjectType enum + subtype strings + metadata families + UI catalog branches | Allowed relations, actor roles, transitions, and schedule semantics are not centrally owned. | Canonical policy/definition | NodeKindRegistry / NodeKindDefinition
Containment hierarchy | Mixed canonical relation | ParentNodeKey + hierarchy-like links in ProjectObjectLinkRecord | Hierarchy semantics are stored twice and then partly reinterpreted as dependency semantics. | Canonical relation | One containment owner (NodeCarrier parent or dedicated containment table)
Non-hierarchy edges | Generic relation table | ProjectObjectLinkRecord | DependsOn / Blocks / BelongsTo / Contains are blurred in one table without explicit policy matrix. | Canonical relation | Explicit NodeEdge / DependencyEdge policy-owned relation model
Spatial semantics | Under-modeled canonical data | PositionX/PositionY on ProjectObjectRecord; markers split between columns and metadata | X/Y matter semantically, but marker ownership is duplicated and mixed with legacy compatibility. | Canonical companion | NodeSpatialSemanticState + NodeMarkerSet (or equivalent)
Typed work item/meeting/participant details | Metadata family payload | ProjectObjectMetadataEnvelope JSON | Typed details are opaque, weakly validated, and partly duplicated in CRM/HR assignment records. | Typed facet / extension | NodeFacet_* records with registry-driven validation
Project/node actor assignment | Duplicated relation | CrmHr ProjectPartyAssignment + node metadata fields + module-local responsible-party fields | The same responsibility truth is written in multiple places with different lifecycles and no single owner. | Canonical cross-cutting relation | ProjectActorAssignment ownership matrix + scoped adapters
Party directory / actor identity | Canonical external identity source | CrmHr party directory / AI agent profile models | Good identity source, but node-level links currently re-store names and IDs in metadata. | Canonical entity | CrmHr identity models + read-only lookups from node scopes
Module-native aggregates | Canonical entities | Projects / Resources / Factory / Validation / TestLab | Workbench currently copies them into persisted system-managed rows instead of assembling from source. | Canonical entities | Stay in native modules; exposed through graph assembly
Assembled project graph | Implicit synced copy | SyncGraphAsync + persisted ProjectObjectRecord/Link rows | Projection cache became effective read truth. | Derived read model / projection | CanonicalGraphAssembler output
Gantt / calendar / summary surfaces | Projection over projection | Workbench structure output | They consume a synced copy instead of one assembled graph. | Derived projections | Projection builders over AssembledProjectGraph
View state | UI state | ProjectWorkbenchViewStateRecord | This separation is mostly healthy and should stay separate from canonical spatial semantics. | UI state | ViewState owner only
LLM/compiler output / embeddings / future vectors | Future derived analytics | Not yet implemented | Must remain proposals / derived semantics, never primary truth. | Derived analytics / proposal layer | Knowledge compiler + semantic index above canonical model

## TruthMap
Truth map
Where the same conceptual truth is currently duplicated and where it should move.
Concern | Current Owner(s) | Duplicate / Drift Surface | Target Owner | Why
Node identity | ProjectObjectRecord.NodeKey + ProjectId | System-managed rows duplicate upstream nodes | Stable Workbench NodeCarrier identity for workbench-authored nodes; external projections assembled on read | Keep node as the stable carrier for brainstorming and typed evolution.
Node type semantics | Enum + subtype strings + UI catalog + metadata family | UI definitions and subtype branching own semantics | NodeKindRegistry | One place must declare allowed transitions, relations, actor roles, time semantics, and UI descriptors.
Hierarchy | ParentNodeKey and relation rows | Hierarchy stored twice; parent chain reused in dependency analysis | Single containment owner | Containment is not the same as dependency.
Dependencies | Generic link table + dependency analysis heuristics | Ancestors treated as prerequisites | Explicit dependency edge model | Critical path logic must be based on explicit edges/policies.
Spatial semantics | PositionX/PositionY on node; markers duplicated | Marker columns and marker metadata both present | Spatial semantic owner + marker owner | X/Y and semantic markers are canonical because the mindmap itself carries meaning.
Work-item assignee | Metadata.WorkItem.AssigneePartyId/Name and ProjectPartyAssignment rows | Two writable truths | Canonical scoped actor-assignment owner | Metadata should not be the authority for live assignments.
Meeting participants | Metadata.Meeting.RelatedParties and ProjectPartyAssignment rows | Two writable truths | Canonical scoped actor-assignment owner | Names can be projected, but membership should have one owner.
Participant directory link | Metadata.Participant.LinkedPartyId/Name and ProjectPartyAssignment rows | Identity link and assignment rows are mixed | Canonical node-to-actor link (or scoped assignment role) | A participant node should link to one actor/party through a canonical relation.
Resource/test/validation responsibility | Module-local ResponsiblePartyId / OwnerPartyId fields | No shared ownership matrix across modules | Explicit ownership matrix + adapters | Do not erase module-native truth blindly; stabilize ownership first.
Structure/calendar/Gantt | Workbench persisted synced rows | Projection acting as truth | Projection builders over assembled graph | Deleting a cache must never change canonical outcomes.

## FeatureClassification
Feature classification
Classification of the CRM/HR wave touchpoints.
File / Area | Classification | Notes
src/CanDoItAll.SharedKernel/ProjectObjectContracts.cs | Domain-core contract | Owns top-level object/link enumerations but not the full semantic policy.
src/CanDoItAll.Modules.Workbench/ProjectWorkbenchModels.cs | Mixed-role application + persistence hotspot | Currently mixes canonical-like data, persistence schema, mutation workflows, and projection read assembly.
src/CanDoItAll.Modules.Workbench/ProjectWorkbenchMetadata.cs | Typed facet payload helper / validation helper | Currently acts as JSON family serializer and partial validator; should shrink once typed facets exist.
src/CanDoItAll.Modules.Workbench/Pages/ProjectStructurePage.PartyIntegration.cs | UI workflow + boundary hotspot | Writes both node metadata and CRM/HR assignment rows, creating duplicated truth.
src/CanDoItAll.Modules.Projects/ProjectPartyIntegrationContracts.cs | Cross-module contract | Good seam, but NodeKey scope is too soft and unconstrained.
src/CanDoItAll.Modules.CrmHr/CrmHrBusinessModels.cs | Canonical identity / assignment persistence | Party directory is strong; node-scoped assignment storage needs stronger scope semantics.
src/CanDoItAll.Modules.CrmHr/CrmHrServices.cs | Application service hotspot | Validates project + party existence but not node existence/project/kind compatibility.
src/CanDoItAll.Modules.Resources/ResourceModels.cs | Module-native canonical aggregate | Owns resource-specific responsibility fields today.
src/CanDoItAll.Modules.Validation/ValidationModels.cs | Module-native canonical aggregate | Owns validation-run responsibility today.
src/CanDoItAll.Modules.TestLab/TestLabModels.cs | Module-native canonical aggregate | Owns test-plan responsibility today.
src/CanDoItAll.Modules.Workbench/ProjectStructureCanvasCatalog.RichDefinitions.cs | UI projection / authoring catalog | Currently owns too much semantic meaning for participant and work-item subtypes.
src/CanDoItAll.Modules.Workbench/Pages/ProjectStructurePage.NodeMutations.cs | UI workflow | Only supports note→block or block→block; does not cover the intended note→task/decision lifecycle.

## NodeEvolution
Node evolution
How brainstorm nodes should evolve while preserving history and semantics.
Scenario | Current State | Target Canonical Model | History Handling | Preservation Rules
Simple brainstorm note | Node of type Note with text only | Workbench-native NodeCarrier with note/simple kind | None or NoteFacet | Keep stable NodeId/NodeKey, title/body, XY, markers, parent, explicit edges
Promote brainstorm to task | UI only supports note→ProjectBlock | Registry-driven transition Note → WorkItem.Task | Create active WorkItemFacet, retire NoteFacet if needed, record NodeTransitionHistory | Preserve spatial semantics; preserve links; optionally retain original note body as history snapshot
Promote brainstorm to decision | Not supported | Registry-driven transition Note → Decision | Create DecisionFacet + transition record | Preserve same node identity so the thought trajectory stays analyzable
Convert task to decision or back | Not modeled | Allowed/disallowed by NodeKindRegistry | Retire/create facets, never destructive delete/recreate by default | Actor assignments are preserved, remapped, or dropped by explicit transition policy
Bind participant node to real person/agent/partner | Metadata + assignment duplication | Canonical node-to-actor link or scoped assignment role | Represent stable identity link without duplicating live truth in metadata | Display names become projection data
Meeting participant edits | Metadata.RelatedParties + assignment rows | Canonical multi-actor link set on meeting scope | Meeting facet reads projected participant names | Meeting node stays stable; links change independently
Cross-module external projection node | Persisted workbench system-managed row | Assembled external projection node | No reclassification by default; create derived workbench follow-up node if needed | Protect external canonical aggregates from accidental mutation through graph editing

## DriftHotspots
Drift hotspots
Files and areas where architectural drift is currently concentrated.
Hotspot | Symptoms | Findings | Why
ProjectWorkbenchModels.cs | 2931 lines; sync, read, write, projection, media, transfer, metadata, links | ACR-001, ACR-002, ACR-004, ACR-005, ACR-006, ACR-008, ACR-009, ACR-010, ACR-014 | Core hotspot
ProjectWorkbenchMetadata.cs | 869 lines; JSON family model, marker normalization, partial validation | ACR-003, ACR-008, ACR-012, ACR-014 | Semantic hotspot
ProjectStructurePage.PartyIntegration.cs | 505 lines; UI writes metadata and assignment rows | ACR-012, ACR-013, ACR-015 | Boundary hotspot
CrmHrServices.cs | 4704 lines overall; assignment save only checks project/party existence | ACR-013, ACR-015 | Cross-module integrity hotspot
ProjectStructureCanvasCatalog.RichDefinitions.cs | UI authoring catalog includes participant/work item semantics | ACR-003, ACR-014 | UI-owned semantics hotspot
Resource/Validation/TestLab responsibility fields | Module-local owner/responsible IDs fragment responsibility truth | ACR-012, ACR-015 | Cross-module drift hotspot

## Validation
Validation plan
Commands Codex must run in a real .NET environment.
Validation Area | Command | Expected Result | Priority
Environment preflight | dotnet --info | Must succeed in the real Codex/.NET environment; blocked in this container. | Required
Solution build | dotnet build CanDoItAll.sln | No compile errors after each phase. | Required
Invariant tests | dotnet test tests/CanDoItAll.Tests.Integration/CanDoItAll.Tests.Integration.csproj --filter "FullyQualifiedName~ProjectWorkbenchServiceIntegrationTests¦FullyQualifiedName~ProjectPartyAssignmentIntegrationTests¦FullyQualifiedName~CrmHrCrossModuleIntegrationTests" | Phase 0-3 targeted guardrails pass. | Required
Component/UI tests | dotnet test tests/CanDoItAll.Tests.Components/CanDoItAll.Tests.Components.csproj --filter "FullyQualifiedName~CrossModuleResponsiblePartyPageTests" | UI flows still bind to the canonical owner. | Required
Playwright smoke for CRM/HR + structure | dotnet test tests/CanDoItAll.Tests.Playwright/CanDoItAll.Tests.Playwright.csproj --filter "FullyQualifiedName~CrmHrCrossModuleFlowTests¦FullyQualifiedName~ProjectPartyAssignmentFlowTests¦FullyQualifiedName~DatabaseSwitchWorkbenchPlaywrightTests" | Cross-module UI/graph behavior works end-to-end. | Recommended
Static skill backcheck | Re-run $canonical-model-review, $feature-block-architecture-review, and $architecture-drift-audit after each phase. | Findings should close or reduce as expected. | Required

## QAReview
QA review
Senior QA inspection of the revised bundle.
Check | Question | Status | Note
QA-01 | Does the updated bundle explicitly reject the 'node is only a view' direction? | Pass | Yes. The target architecture now keeps node as the stable universal carrier for workbench-authored thinking.
QA-02 | Are X/Y and markers treated as semantically meaningful canonical data? | Pass | Yes. Spatial semantics are separated from ephemeral view-state and retained as canonical companion data.
QA-03 | Does the bundle cover CRM/HR duplication and node-scoped assignment integrity? | Pass | Yes. ACR-012, ACR-013, and ACR-015 add direct remediation and tests.
QA-04 | Does the bundle define how brainstorm notes become typed work without losing history? | Pass | Yes. ACR-014 prescribes stable node identity with facet transitions and transition history.
QA-05 | Is there any place where the bundle still implies destructive delete/recreate as the default transition? | Pass after amendment | The final architecture forbids destructive delete/recreate as the default for workbench-native node evolution.
QA-06 | Can Codex execute this bundle phase-by-phase without a full rewrite? | Pass with caution | Yes, but dotnet runtime execution is blocked in this container; implementation-time validation is mandatory.

## SubbundleIndex
Subbundle index
One execution packet per finding.
Subbundle Path | Finding | Severity | Phase | Skill Source
subbundles/ACR-005-workbench-reparent-flow-lacks-explicit-cycle-and-parent-invariants | ACR-005 | Critical | Phase 0 | feature-block-architecture-review
subbundles/ACR-011-core-canonical-invariant-and-projection-equivalence-tests-are-missing | ACR-011 | High | Phase 0 | canonical-model-review
subbundles/ACR-013-node-scoped-crm-hr-assignments-use-a-soft-nodekey-reference-without-cano | ACR-013 | High | Phase 0 | feature-block-architecture-review
subbundles/ACR-012-party-responsibility-truth-is-duplicated-across-node-metadata-assignment | ACR-012 | Critical | Phase 1 | canonical-model-review
subbundles/ACR-003-type-and-subtype-semantics-are-weak-and-partly-owned-by-the-ui-catalog | ACR-003 | High | Phase 1 | canonical-model-review
subbundles/ACR-004-relation-semantics-are-blurred-and-hierarchy-is-stored-twice | ACR-004 | High | Phase 1 | canonical-model-review
subbundles/ACR-001-persisted-system-managed-workbench-graph-acts-as-a-parallel-truth | ACR-001 | Critical | Phase 2 | canonical-model-review
subbundles/ACR-006-calendar-and-gantt-are-projections-over-a-persisted-projection | ACR-006 | High | Phase 2 | canonical-model-review
subbundles/ACR-014-node-reclassification-and-typed-lifecycle-history-are-insufficient-for-n | ACR-014 | High | Phase 2 | feature-block-architecture-review
subbundles/ACR-002-projectobjectrecord-is-an-overloaded-universal-box | ACR-002 | High | Phase 3 | canonical-model-review
subbundles/ACR-008-spatial-semantics-are-canonical-but-marker-ownership-is-duplicated-and-u | ACR-008 | High | Phase 3 | canonical-model-review
subbundles/ACR-015-cross-module-responsibility-model-is-fragmented-and-lacks-one-canonical | ACR-015 | High | Phase 3 | canonical-model-review
subbundles/ACR-007-route-artifact-binding-and-storage-media-concerns-leak-into-node-truth | ACR-007 | Medium | Phase 3 | canonical-model-review
subbundles/ACR-009-projectworkbenchservice-is-an-oversized-orchestration-hotspot | ACR-009 | High | Phase 4 | architecture-drift-audit
subbundles/ACR-010-lease-scope-granularity-does-not-match-mutation-granularity | ACR-010 | Medium | Phase 4 | architecture-drift-audit