## Overview
Skill Tool MCP Isolation Plan | Skill Tool MCP Isolation Plan | Skill Tool MCP Isolation Plan | Skill Tool MCP Isolation Plan | Skill Tool MCP Isolation Plan | Skill Tool MCP Isolation Plan | Skill Tool MCP Isolation Plan
Prepared initiative workbook for isolating Skill, Tool, and MCP capability definitions from MAF and seed code while adding typed agent/process/workflow/UI restrictions, preserving existing behavior, and keeping setup diagnostics repairable. | Prepared initiative workbook for isolating Skill, Tool, and MCP capability definitions from MAF and seed code while adding typed agent/process/workflow/UI restrictions, preserving existing behavior, and keeping setup diagnostics repairable. | Prepared initiative workbook for isolating Skill, Tool, and MCP capability definitions from MAF and seed code while adding typed agent/process/workflow/UI restrictions, preserving existing behavior, and keeping setup diagnostics repairable. | Prepared initiative workbook for isolating Skill, Tool, and MCP capability definitions from MAF and seed code while adding typed agent/process/workflow/UI restrictions, preserving existing behavior, and keeping setup diagnostics repairable. | Prepared initiative workbook for isolating Skill, Tool, and MCP capability definitions from MAF and seed code while adding typed agent/process/workflow/UI restrictions, preserving existing behavior, and keeping setup diagnostics repairable. | Prepared initiative workbook for isolating Skill, Tool, and MCP capability definitions from MAF and seed code while adding typed agent/process/workflow/UI restrictions, preserving existing behavior, and keeping setup diagnostics repairable. | Prepared initiative workbook for isolating Skill, Tool, and MCP capability definitions from MAF and seed code while adding typed agent/process/workflow/UI restrictions, preserving existing behavior, and keeping setup diagnostics repairable.
Metric | Value | Status | Risk | Gate | Owner | Notes
Bundle profile | initiative | Prepared | Medium | Prepared-stage validator | Architecture | Long-run migration with runtime and UI impacts
Subbundles | 12 | Ready | Medium | SB01 before implementation | Delivery | Contracts, schema, access policy, and exposure descriptors first
Mandatory checkpoints | 3 | Added | High | SB05/SB07/SB09 | Architecture | Hardening blocks templates, MAF reconnection, and UI/API
Critical foundations | 6 | Defined | High | Semantic proof required | Delivery | SB01-SB06 plus MCP/tool proof
Access policy model | Typed effective set | Added | High | SB01/SB05/SB08 | Architecture | Restrictions deny/require assigned candidates without raw runtime strings
UI/e2e gates | 2 | Planned | High | Playwright required | QA | SB10 and SB11
Codeanalytics snapshot | snap-20260628122504-1aa0230f | Captured | Medium | Runtime hardening | Architecture | MAF type cycle and large-file pressure identified
Production code | None changed | Compliant | Low | Preparation only | Codex | No implementation in this turn
Workbook validation | Render previews | Required | Low | Visual inspection | Codex | PNG previews generated from workbook sheets
Architecture Rule: Do not reconnect MAF until contracts, access policy, dedicated implementations, SB05 hardening, template loading, SB07 seed/policy hardening, and setup tests have proof. MAF must consume EffectiveCapabilitySet instead of hidden filters. | Architecture Rule: Do not reconnect MAF until contracts, access policy, dedicated implementations, SB05 hardening, template loading, SB07 seed/policy hardening, and setup tests have proof. MAF must consume EffectiveCapabilitySet instead of hidden filters. | Architecture Rule: Do not reconnect MAF until contracts, access policy, dedicated implementations, SB05 hardening, template loading, SB07 seed/policy hardening, and setup tests have proof. MAF must consume EffectiveCapabilitySet instead of hidden filters. | Architecture Rule: Do not reconnect MAF until contracts, access policy, dedicated implementations, SB05 hardening, template loading, SB07 seed/policy hardening, and setup tests have proof. MAF must consume EffectiveCapabilitySet instead of hidden filters. | Architecture Rule: Do not reconnect MAF until contracts, access policy, dedicated implementations, SB05 hardening, template loading, SB07 seed/policy hardening, and setup tests have proof. MAF must consume EffectiveCapabilitySet instead of hidden filters. | Architecture Rule: Do not reconnect MAF until contracts, access policy, dedicated implementations, SB05 hardening, template loading, SB07 seed/policy hardening, and setup tests have proof. MAF must consume EffectiveCapabilitySet instead of hidden filters. | Architecture Rule: Do not reconnect MAF until contracts, access policy, dedicated implementations, SB05 hardening, template loading, SB07 seed/policy hardening, and setup tests have proof. MAF must consume EffectiveCapabilitySet instead of hidden filters.

## Phase Flow
Phase Flow And Gates | Phase Flow And Gates | Phase Flow And Gates | Phase Flow And Gates | Phase Flow And Gates | Phase Flow And Gates
Execution order, dependencies, and proof gates. SB05, SB07, and SB09 are mandatory hardening checkpoints. | Execution order, dependencies, and proof gates. SB05, SB07, and SB09 are mandatory hardening checkpoints. | Execution order, dependencies, and proof gates. SB05, SB07, and SB09 are mandatory hardening checkpoints. | Execution order, dependencies, and proof gates. SB05, SB07, and SB09 are mandatory hardening checkpoints. | Execution order, dependencies, and proof gates. SB05, SB07, and SB09 are mandatory hardening checkpoints. | Execution order, dependencies, and proof gates. SB05, SB07, and SB09 are mandatory hardening checkpoints.
ID | Subbundle | Validation Depth | Prerequisites | Deliverables | Proof Gate
SB01 | Contracts + Template Schema + Access Policy + Error Model | Critical foundation | None | Typed descriptors, exposure descriptors, access policy contracts, setup results, structured diagnostics | Schema/naming/access-policy/diagnostics unit tests; proof/SB01
SB02 | Tooling Abstractions + Implementations | Critical foundation | SB01 | Internal tools, external process/http invokers, policy metadata, tool exposure descriptors | Unit/integration call proof; policy, exposure, and error parity
SB03 | Skills Abstractions + Loader | Critical foundation | SB01 | File/inline/registered skill loader, script policy, skill exposure descriptors | Skill loader and exposure descriptor unit/integration proof
SB04 | MCP Abstractions + Runtime | Critical foundation | SB01 | Internal/local/remote MCP lifecycle, setup test, server/tool exposure descriptors | Fake MCP start/list/call/stop, exposure, and failure proof
SB05 | Capability Core Hardening Checkpoint | Mandatory checkpoint | SB02-SB04 | Refactor, access evaluator, diagnostics, performance scan, no MAF/UI dependencies | Hardening manifest, static scan, negative and suppression tests
SB06 | Template Loading + Seeding | Critical foundation | SB05 | Templates/Capabilities, access policy loader, seed materializer | Seed parity, operation compatibility, and no-fallback integration proof
SB07 | Template/Seed/Policy Hardening Checkpoint | Mandatory checkpoint | SB06 | Parity, managed seed dry-run, policy diagnostics, deterministic failures | No-fallback, policy validation, seed stability, performance proof
SB08 | MAF Reconnection + Compatibility | Critical runtime | SB07 | MAF adapters consume isolated services and EffectiveCapabilitySet | Runtime composition, suppression, and diagnostics propagation proof
SB09 | Runtime Hardening + Optimization Checkpoint | Mandatory checkpoint | SB08 | Thin adapters, no hidden filters, cycle review, cleanup/cancellation, performance scan | Runtime hardening, hidden-filter scan, and codeanalytics/static scan
SB10 | UI/API Setup + Access Policy Flows | Critical UI | SB09 | Tool setup, MCP list-tools, access policy editor/preview, repairable errors | API, component, Playwright proof
SB11 | Regression Proof | Closure critical | SB09-SB10 | Process/workflow behavior parity, restrictions, and setup failure proof | Unit/integration/component/e2e matrix
SB12 | Cleanup + Docs | Final closure | SB11 | Remove obsolete hardcoded paths, hidden filters, and document workflow | Final build/test/static search/docs

## Subbundle Checklist
Subbundle Checklist | Subbundle Checklist | Subbundle Checklist | Subbundle Checklist | Subbundle Checklist | Subbundle Checklist | Subbundle Checklist | Subbundle Checklist
Detailed execution checklist. Status values are initialized to Not Started because implementation has not begun. | Detailed execution checklist. Status values are initialized to Not Started because implementation has not begun. | Detailed execution checklist. Status values are initialized to Not Started because implementation has not begun. | Detailed execution checklist. Status values are initialized to Not Started because implementation has not begun. | Detailed execution checklist. Status values are initialized to Not Started because implementation has not begun. | Detailed execution checklist. Status values are initialized to Not Started because implementation has not begun. | Detailed execution checklist. Status values are initialized to Not Started because implementation has not begun. | Detailed execution checklist. Status values are initialized to Not Started because implementation has not begun.
ID | Subbundle | Checklist Item | Dependency | Status | Required Action | Owner | Validation Depth
SB01 | Contracts + Template Schema + Access Policy + Error Model | Entry Gate | None | Not Started | Confirm prerequisites, source refs, and previous proof | Execution agent | Critical foundation
SB01 | Contracts + Template Schema + Access Policy + Error Model | Implementation | Entry Gate | Not Started | Make minimal scoped code changes | Execution agent | Critical foundation
SB01 | Contracts + Template Schema + Access Policy + Error Model | Negative Proof | Implementation | Not Started | Exercise error/failure cases required by subbundle | Execution agent | Critical foundation
SB01 | Contracts + Template Schema + Access Policy + Error Model | Unit Proof | Implementation | Not Started | Run focused unit tests | Execution agent | Critical foundation
SB01 | Contracts + Template Schema + Access Policy + Error Model | Integration/E2E Proof | Unit Proof | Not Started | Run required integration, component, or Playwright proof | QA agent | Critical foundation
SB01 | Contracts + Template Schema + Access Policy + Error Model | Closure Gate | All proof | Not Started | Update proof manifest and execution report | Execution agent | Critical foundation
SB02 | Tooling Abstractions + Implementations | Entry Gate | SB01 | Not Started | Confirm prerequisites, source refs, and previous proof | Execution agent | Critical foundation
SB02 | Tooling Abstractions + Implementations | Implementation | Entry Gate | Not Started | Make minimal scoped code changes | Execution agent | Critical foundation
SB02 | Tooling Abstractions + Implementations | Negative Proof | Implementation | Not Started | Exercise error/failure cases required by subbundle | Execution agent | Critical foundation
SB02 | Tooling Abstractions + Implementations | Unit Proof | Implementation | Not Started | Run focused unit tests | Execution agent | Critical foundation
SB02 | Tooling Abstractions + Implementations | Integration/E2E Proof | Unit Proof | Not Started | Run required integration, component, or Playwright proof | QA agent | Critical foundation
SB02 | Tooling Abstractions + Implementations | Closure Gate | All proof | Not Started | Update proof manifest and execution report | Execution agent | Critical foundation
SB03 | Skills Abstractions + Loader | Entry Gate | SB01 | Not Started | Confirm prerequisites, source refs, and previous proof | Execution agent | Critical foundation
SB03 | Skills Abstractions + Loader | Implementation | Entry Gate | Not Started | Make minimal scoped code changes | Execution agent | Critical foundation
SB03 | Skills Abstractions + Loader | Negative Proof | Implementation | Not Started | Exercise error/failure cases required by subbundle | Execution agent | Critical foundation
SB03 | Skills Abstractions + Loader | Unit Proof | Implementation | Not Started | Run focused unit tests | Execution agent | Critical foundation
SB03 | Skills Abstractions + Loader | Integration/E2E Proof | Unit Proof | Not Started | Run required integration, component, or Playwright proof | QA agent | Critical foundation
SB03 | Skills Abstractions + Loader | Closure Gate | All proof | Not Started | Update proof manifest and execution report | Execution agent | Critical foundation
SB04 | MCP Abstractions + Runtime | Entry Gate | SB01 | Not Started | Confirm prerequisites, source refs, and previous proof | Execution agent | Critical foundation
SB04 | MCP Abstractions + Runtime | Implementation | Entry Gate | Not Started | Make minimal scoped code changes | Execution agent | Critical foundation
SB04 | MCP Abstractions + Runtime | Negative Proof | Implementation | Not Started | Exercise error/failure cases required by subbundle | Execution agent | Critical foundation
SB04 | MCP Abstractions + Runtime | Unit Proof | Implementation | Not Started | Run focused unit tests | Execution agent | Critical foundation
SB04 | MCP Abstractions + Runtime | Integration/E2E Proof | Unit Proof | Not Started | Run required integration, component, or Playwright proof | QA agent | Critical foundation
SB04 | MCP Abstractions + Runtime | Closure Gate | All proof | Not Started | Update proof manifest and execution report | Execution agent | Critical foundation
SB05 | Capability Core Hardening Checkpoint | Entry Gate | SB02-SB04 | Not Started | Confirm prerequisites, source refs, and previous proof | Execution agent | Mandatory checkpoint
SB05 | Capability Core Hardening Checkpoint | Implementation | Entry Gate | Not Started | Make minimal scoped code changes | Execution agent | Mandatory checkpoint
SB05 | Capability Core Hardening Checkpoint | Negative Proof | Implementation | Not Started | Exercise error/failure cases required by subbundle | Execution agent | Mandatory checkpoint
SB05 | Capability Core Hardening Checkpoint | Unit Proof | Implementation | Not Started | Run focused unit tests | Execution agent | Mandatory checkpoint
SB05 | Capability Core Hardening Checkpoint | Integration/E2E Proof | Unit Proof | Not Started | Run required integration, component, or Playwright proof | QA agent | Mandatory checkpoint
SB05 | Capability Core Hardening Checkpoint | Closure Gate | All proof | Not Started | Update proof manifest and execution report | Execution agent | Mandatory checkpoint
SB06 | Template Loading + Seeding | Entry Gate | SB05 | Not Started | Confirm prerequisites, source refs, and previous proof | Execution agent | Critical foundation
SB06 | Template Loading + Seeding | Implementation | Entry Gate | Not Started | Make minimal scoped code changes | Execution agent | Critical foundation
SB06 | Template Loading + Seeding | Negative Proof | Implementation | Not Started | Exercise error/failure cases required by subbundle | Execution agent | Critical foundation
SB06 | Template Loading + Seeding | Unit Proof | Implementation | Not Started | Run focused unit tests | Execution agent | Critical foundation
SB06 | Template Loading + Seeding | Integration/E2E Proof | Unit Proof | Not Started | Run required integration, component, or Playwright proof | QA agent | Critical foundation
SB06 | Template Loading + Seeding | Closure Gate | All proof | Not Started | Update proof manifest and execution report | Execution agent | Critical foundation
SB07 | Template/Seed/Policy Hardening Checkpoint | Entry Gate | SB06 | Not Started | Confirm prerequisites, source refs, and previous proof | Execution agent | Mandatory checkpoint
SB07 | Template/Seed/Policy Hardening Checkpoint | Implementation | Entry Gate | Not Started | Make minimal scoped code changes | Execution agent | Mandatory checkpoint
SB07 | Template/Seed/Policy Hardening Checkpoint | Negative Proof | Implementation | Not Started | Exercise error/failure cases required by subbundle | Execution agent | Mandatory checkpoint
SB07 | Template/Seed/Policy Hardening Checkpoint | Unit Proof | Implementation | Not Started | Run focused unit tests | Execution agent | Mandatory checkpoint
SB07 | Template/Seed/Policy Hardening Checkpoint | Integration/E2E Proof | Unit Proof | Not Started | Run required integration, component, or Playwright proof | QA agent | Mandatory checkpoint
SB07 | Template/Seed/Policy Hardening Checkpoint | Closure Gate | All proof | Not Started | Update proof manifest and execution report | Execution agent | Mandatory checkpoint
SB08 | MAF Reconnection + Compatibility | Entry Gate | SB07 | Not Started | Confirm prerequisites, source refs, and previous proof | Execution agent | Critical runtime
SB08 | MAF Reconnection + Compatibility | Implementation | Entry Gate | Not Started | Make minimal scoped code changes | Execution agent | Critical runtime
SB08 | MAF Reconnection + Compatibility | Negative Proof | Implementation | Not Started | Exercise error/failure cases required by subbundle | Execution agent | Critical runtime
SB08 | MAF Reconnection + Compatibility | Unit Proof | Implementation | Not Started | Run focused unit tests | Execution agent | Critical runtime
SB08 | MAF Reconnection + Compatibility | Integration/E2E Proof | Unit Proof | Not Started | Run required integration, component, or Playwright proof | QA agent | Critical runtime
SB08 | MAF Reconnection + Compatibility | Closure Gate | All proof | Not Started | Update proof manifest and execution report | Execution agent | Critical runtime
SB09 | Runtime Hardening + Optimization Checkpoint | Entry Gate | SB08 | Not Started | Confirm prerequisites, source refs, and previous proof | Execution agent | Mandatory checkpoint
SB09 | Runtime Hardening + Optimization Checkpoint | Implementation | Entry Gate | Not Started | Make minimal scoped code changes | Execution agent | Mandatory checkpoint
SB09 | Runtime Hardening + Optimization Checkpoint | Negative Proof | Implementation | Not Started | Exercise error/failure cases required by subbundle | Execution agent | Mandatory checkpoint
SB09 | Runtime Hardening + Optimization Checkpoint | Unit Proof | Implementation | Not Started | Run focused unit tests | Execution agent | Mandatory checkpoint
SB09 | Runtime Hardening + Optimization Checkpoint | Integration/E2E Proof | Unit Proof | Not Started | Run required integration, component, or Playwright proof | QA agent | Mandatory checkpoint
SB09 | Runtime Hardening + Optimization Checkpoint | Closure Gate | All proof | Not Started | Update proof manifest and execution report | Execution agent | Mandatory checkpoint
SB10 | UI/API Setup + Access Policy Flows | Entry Gate | SB09 | Not Started | Confirm prerequisites, source refs, and previous proof | Execution agent | Critical UI
SB10 | UI/API Setup + Access Policy Flows | Implementation | Entry Gate | Not Started | Make minimal scoped code changes | Execution agent | Critical UI
SB10 | UI/API Setup + Access Policy Flows | Negative Proof | Implementation | Not Started | Exercise error/failure cases required by subbundle | Execution agent | Critical UI
SB10 | UI/API Setup + Access Policy Flows | Unit Proof | Implementation | Not Started | Run focused unit tests | Execution agent | Critical UI
SB10 | UI/API Setup + Access Policy Flows | Integration/E2E Proof | Unit Proof | Not Started | Run required integration, component, or Playwright proof | QA agent | Critical UI
SB10 | UI/API Setup + Access Policy Flows | Closure Gate | All proof | Not Started | Update proof manifest and execution report | Execution agent | Critical UI
SB11 | Regression Proof | Entry Gate | SB09-SB10 | Not Started | Confirm prerequisites, source refs, and previous proof | Execution agent | Closure critical
SB11 | Regression Proof | Implementation | Entry Gate | Not Started | Make minimal scoped code changes | Execution agent | Closure critical
SB11 | Regression Proof | Negative Proof | Implementation | Not Started | Exercise error/failure cases required by subbundle | Execution agent | Closure critical
SB11 | Regression Proof | Unit Proof | Implementation | Not Started | Run focused unit tests | Execution agent | Closure critical
SB11 | Regression Proof | Integration/E2E Proof | Unit Proof | Not Started | Run required integration, component, or Playwright proof | QA agent | Closure critical
SB11 | Regression Proof | Closure Gate | All proof | Not Started | Update proof manifest and execution report | Execution agent | Closure critical
SB12 | Cleanup + Docs | Entry Gate | SB11 | Not Started | Confirm prerequisites, source refs, and previous proof | Execution agent | Final closure
SB12 | Cleanup + Docs | Implementation | Entry Gate | Not Started | Make minimal scoped code changes | Execution agent | Final closure
SB12 | Cleanup + Docs | Negative Proof | Implementation | Not Started | Exercise error/failure cases required by subbundle | Execution agent | Final closure
SB12 | Cleanup + Docs | Unit Proof | Implementation | Not Started | Run focused unit tests | Execution agent | Final closure
SB12 | Cleanup + Docs | Integration/E2E Proof | Unit Proof | Not Started | Run required integration, component, or Playwright proof | QA agent | Final closure
SB12 | Cleanup + Docs | Closure Gate | All proof | Not Started | Update proof manifest and execution report | Execution agent | Final closure

## Testing Matrix
Unit Integration Component E2E Matrix | Unit Integration Component E2E Matrix | Unit Integration Component E2E Matrix | Unit Integration Component E2E Matrix | Unit Integration Component E2E Matrix | Unit Integration Component E2E Matrix | Unit Integration Component E2E Matrix
Test split required by the bundle. UI, process/workflow behavior, and setup failures require component and Playwright proof. | Test split required by the bundle. UI, process/workflow behavior, and setup failures require component and Playwright proof. | Test split required by the bundle. UI, process/workflow behavior, and setup failures require component and Playwright proof. | Test split required by the bundle. UI, process/workflow behavior, and setup failures require component and Playwright proof. | Test split required by the bundle. UI, process/workflow behavior, and setup failures require component and Playwright proof. | Test split required by the bundle. UI, process/workflow behavior, and setup failures require component and Playwright proof. | Test split required by the bundle. UI, process/workflow behavior, and setup failures require component and Playwright proof.
Subbundle | Unit Tests | Integration Tests | Component Tests | E2E Tests | Proof Artifacts | Risk If Missing
SB01 | Schema, naming, access policy conversion/precedence, diagnostics, invalid templates | Pack load smoke | N/A | N/A | proof/SB01 | Later projects duplicate DTOs or accept stringly/bad templates
SB02 | Internal/external invokers, exposure descriptors, timeout, masking, schema | Representative tool family composition | N/A | External tool setup via SB10 | proof/SB02 | Process tools regress or unsafe external execution leaks in
SB03 | File/inline/registered skill loader and exposure descriptors | Seeded skill load parity | N/A | Skill setup via SB10 | proof/SB03 | Default skills fail or load from hidden fallbacks
SB04 | MCP lifecycle, list-tools, exposure descriptors, secret rejection | Fake MCP start/list/call/stop | N/A | MCP setup via SB10 | proof/SB04 | MCP processes leak or setup cannot prove tools
SB05 | Diagnostics, access evaluator, file-size, dependency, allocation guard tests | Isolated service composition and suppression smoke | N/A | N/A | proof/SB05 | Happy-path-only capability services feed templates/runtime
SB06 | Template materializer and access policy validation | Seed parity, operation compatibility, and agent assignment resolution | N/A | Seeded capability list via SB11 | proof/SB06 | Templates ignored while hardcoded defaults still pass
SB07 | Template/policy failure taxonomy and managed seed guards | Migration dry-run, operation compatibility, and parity proof | N/A | N/A | proof/SB07 | MAF reconnects to unstable seed/template/policy behavior
SB08 | MAF adapter, effective set, and diagnostics propagation tests | Runtime composition and suppression through new services | N/A | Process smoke via SB11 | proof/SB08 | MAF stays coupled under new names
SB09 | Runtime diagnostics, cleanup, no-fallback/no-hidden-filter, performance guards | Runtime composition and cleanup proof | N/A | N/A | proof/SB09 | UI/API builds on a brittle runtime
SB10 | Setup service and access policy preview tests | API setup-test and policy endpoints | Wizard/editor/access-policy bUnit tests | Tool + MCP setup, policy preview, and failure flows | proof/SB10 | Users cannot test, restrict, or repair capabilities safely
SB11 | Access policy regression | Process/workflow runtime tests with restrictions | Capability panel and policy editor regression | Full setup/runtime/restriction smoke | proof/SB11 | Behavior changed without evidence
SB12 | Guard tests for fallbacks and hidden filters | Final build/test | Conditional final UI smoke | Conditional final e2e | proof/SB12 | Old hardcoded paths or suppressors remain active

## Reconnection Map
Reconnection Map | Reconnection Map | Reconnection Map | Reconnection Map | Reconnection Map
Existing hardcoded surfaces and their planned new owners. Reconnection happens after foundation and template hardening proof. | Existing hardcoded surfaces and their planned new owners. Reconnection happens after foundation and template hardening proof. | Existing hardcoded surfaces and their planned new owners. Reconnection happens after foundation and template hardening proof. | Existing hardcoded surfaces and their planned new owners. Reconnection happens after foundation and template hardening proof. | Existing hardcoded surfaces and their planned new owners. Reconnection happens after foundation and template hardening proof.
Existing Surface | Current Responsibility | New Owner | Subbundle | Regression Focus
MafAgentRuntime.Capabilities.cs | Composition and nested config models | MAF adapter over capability services | SB08/SB09 | Runtime composition and diagnostics
MafAgentRuntime.Capabilities.Tools.cs | String switch to AIFunctionFactory | Tools implementation plus adapter | SB02/SB05/SB08 | Tool name and policy parity
MafAgentRuntime.Capabilities.Skills.cs | File/inline/registered skill loading | Skills loader plus adapter | SB03/SB05/SB08 | Skill activation parity
MafAgentRuntime.Capabilities.Mcp.cs | MCP client startup, allowed tools, secrets | MCP runtime plus adapter | SB04/SB05/SB08 | List-tools and cleanup proof
AgentCapabilityRequirementEvaluator | Required capability checks only | Capability access evaluator with denied-required diagnostics | SB01/SB05/SB08 | Required plus denied proof
ProcessToolOperationAuthorizer | Tool-only string operation gating | Typed operation selectors feeding shared access policy | SB01/SB06/SB08 | AllowedOperations compatibility
AgentRuntimeContextIntent | AllowedOperations strings and coarse flags | Typed access policy snapshot/effective context | SB01/SB06/SB08 | Process/workflow restriction parity
SandboxWorkspaceSeedBuilder | Hardcoded default capability catalog | Templates/Capabilities materializer | SB06/SB07 | Seed parity and no fallback
CapabilityProofService | Kind-specific structural proof | Setup-test services | SB04/SB10 | Live test result parity
CapabilitySetupWizardDialog | Skill/MCP-only setup | Skill/Tool/MCP setup and access-policy editor UI | SB10 | Component and Playwright proof
AgentsApi capability endpoints | Generic CRUD/verify | Setup-test and policy preview endpoints | SB10 | API integration proof
Old hardcoded cleanup | Legacy active paths | Documented compatibility or removal | SB12 | Guard tests and static search

## Template Schema
Template Pack Schema | Template Pack Schema | Template Pack Schema | Template Pack Schema | Template Pack Schema | Template Pack Schema
Proposed Templates/Capabilities pack shape, required fields, setup-test declarations, and failure categories. | Proposed Templates/Capabilities pack shape, required fields, setup-test declarations, and failure categories. | Proposed Templates/Capabilities pack shape, required fields, setup-test declarations, and failure categories. | Proposed Templates/Capabilities pack shape, required fields, setup-test declarations, and failure categories. | Proposed Templates/Capabilities pack shape, required fields, setup-test declarations, and failure categories. | Proposed Templates/Capabilities pack shape, required fields, setup-test declarations, and failure categories.
Template Area | Descriptor Types | Required Fields | Validation Rules | Security Rule | Owning Subbundle
Common | skill, tool, mcpServer | key, kind, stableIdKey, displayName, description, tags, operation classifications, configuration | Duplicate keys and invalid names fail with path/key/field | No raw secrets | SB01/SB06
Skills | file, inline, registered | skillRoot or inline instructions or registered descriptor | SKILL.md name/description required | Script policy explicit | SB03/SB06
Tools | internal, externalProcess, externalHttp, providerNative | runtimeName, schema, operation, sideEffect, approval | Input/output schema and setup test required | Timeout and bindings required | SB02/SB06
MCPs | internalHosted, localStdio, remoteHttp | transport, lifecycle, allowedTools, approvalMode | List-tools setup test required | Raw env/header rejected | SB04/SB06
Diagnostics | validation, setup, runtime call | category, key, kind, correlationId, maskedDetail, repairHint | Generic errors rejected | Bounded output excerpts | SB01-SB11
Access Policies | agent, process, processStep, workflow, workflowNode | effect, scope, selector kind/value, reason | Invalid selectors, ambiguous MCP tools, and grant attempts fail before materialization | Deny restricts assigned candidates only | SB01/SB06/SB10
Policies | tool-policy, approval-defaults | classification, process requirements, target scope | Policy parity with old registry | High-risk tools approval-gated | SB01/SB02
Compatibility | aliases, stable IDs | old key/name, new key/name, migration note | No silent renames | Explicit migration only | SB06/SB12

## Access Policy
Capability Access Policy | Capability Access Policy | Capability Access Policy | Capability Access Policy | Capability Access Policy | Capability Access Policy | Capability Access Policy
Typed restriction model for agents, processes, workflows, UI preview, and MAF runtime composition. | Typed restriction model for agents, processes, workflows, UI preview, and MAF runtime composition. | Typed restriction model for agents, processes, workflows, UI preview, and MAF runtime composition. | Typed restriction model for agents, processes, workflows, UI preview, and MAF runtime composition. | Typed restriction model for agents, processes, workflows, UI preview, and MAF runtime composition. | Typed restriction model for agents, processes, workflows, UI preview, and MAF runtime composition. | Typed restriction model for agents, processes, workflows, UI preview, and MAF runtime composition.
Area | Design Rule | Typed Model | Template/UI Boundary | Runtime Behavior | Proof | Owner
Candidate set | Policy starts from assigned/enabled capabilities | EffectiveCapabilitySet | UI may preview assigned candidates | Allow does not grant unassigned capabilities | Unit precedence test | SB01/SB05
Exposure | Every capability exposes common metadata | CapabilityExposureDescriptor | Catalog-backed selectors | New capabilities participate by descriptor | Fake future capability test | SB02-SB05
Selectors | Use bounded selector kinds only | CapabilitySelector | kind, key, tag, operation, runtime tool, MCP server/tool | No regex/script policy language | Selector matching tests | SB01
Precedence | Deny wins over allow; system deny wins globally | CapabilityAccessRule | Rule order is readability only | Deterministic diagnostics | Precedence tests | SB01/SB05
Requirements | Required denied capability is explicit failure | SuppressedCapabilityDiagnostic | Reason is required for deny/require | Run blocks with repair hint | Denied-required integration test | SB08/SB11
Process operations | Old AllowedOperations compile once to typed selectors | ProcessOperationKey | Templates keep text boundary | No attach-time string comparisons | Compatibility tests | SB06/SB09
MCP child tools | MCP tool selector must include server context | McpServerKey + McpToolName | List-tools fills picker choices | Server and child tool can be denied separately | Setup plus process denial e2e | SB04/SB10/SB11
Diagnostics | Suppression must be visible and repairable | SuppressedCapabilityDiagnostic | UI/API shows rule scope, selector, reason | Manifest records excluded source | API/UI assertions | SB08-SB11

## Error States
External Tool And MCP Error States | External Tool And MCP Error States | External Tool And MCP Error States | External Tool And MCP Error States | External Tool And MCP Error States | External Tool And MCP Error States
Concrete negative cases that must produce structured, masked, repairable diagnostics. | Concrete negative cases that must produce structured, masked, repairable diagnostics. | Concrete negative cases that must produce structured, masked, repairable diagnostics. | Concrete negative cases that must produce structured, masked, repairable diagnostics. | Concrete negative cases that must produce structured, masked, repairable diagnostics. | Concrete negative cases that must produce structured, masked, repairable diagnostics.
Area | Failure | Required Diagnostic | Test Layer | Owning Subbundle | Blocks
External process tool | Executable not found | path, working directory, capability key, category ProcessStart, repair hint | Unit/API | SB02/SB10 | SB05/SB11
External process tool | Timeout | configured timeout, elapsed time, bounded stdout/stderr, cleanup result | Unit/API | SB02/SB10 | SB05/SB11
External process tool | Non-zero exit or invalid JSON | exit code, bounded output, JsonParse or SchemaValidation category | Unit/API | SB02/SB10 | SB05/SB11
External HTTP tool | Missing secret or non-success status | binding key or status code, masked headers, bounded response | Unit/API | SB02/SB10 | SB05/SB11
Local stdio MCP | Process exits before handshake | exit code, bounded stdout/stderr, startup phase, cleanup result | Integration/API | SB04/SB10 | SB05/SB11
MCP list-tools | List fails or allowedTools mismatch | server key, discovered names, missing/extra names, repair hint | Integration/UI | SB04/SB10 | SB05/SB11
Capability access policy | Invalid selector or unknown key | template path, field path, bad value, allowed examples, repair hint | Unit/API/UI | SB01/SB06/SB10 | SB07/SB11
Capability access policy | Required capability denied | required source, denying scope, selector, reason, repair hint | Unit/Integration/E2E | SB05/SB08/SB11 | SB09/SB11
Capability access policy | MCP child tool ambiguous | server context requirement, candidate servers, field path, repair hint | Unit/API/UI | SB01/SB04/SB10 | SB07/SB11
Template loader | Duplicate key or missing field | template path, key, field path, category TemplateValidation | Unit/Integration | SB01/SB06/SB07 | SB08
Runtime adapter | Underlying failure propagation | original category, capability key/kind, correlation ID preserved | Unit/Integration | SB08/SB09 | SB10

## Hardening Gates
Hardening And Optimization Gates | Hardening And Optimization Gates | Hardening And Optimization Gates | Hardening And Optimization Gates | Hardening And Optimization Gates | Hardening And Optimization Gates
Mandatory checkpoints that block the next phase until refactoring, diagnostics, and performance concerns are handled. | Mandatory checkpoints that block the next phase until refactoring, diagnostics, and performance concerns are handled. | Mandatory checkpoints that block the next phase until refactoring, diagnostics, and performance concerns are handled. | Mandatory checkpoints that block the next phase until refactoring, diagnostics, and performance concerns are handled. | Mandatory checkpoints that block the next phase until refactoring, diagnostics, and performance concerns are handled. | Mandatory checkpoints that block the next phase until refactoring, diagnostics, and performance concerns are handled.
Checkpoint | Must Prove | Static/Perf Scan | Negative Tests | Blocks | Risk If Skipped
SB05 | Isolated tools/skills/MCPs and access evaluator are split, mockable, and independent of MAF/UI | file size, dependency direction, serializer options, LINQ/collections, cancellation, policy parsing | external tool failure, skill missing, MCP startup/list failure, denied required capability | SB06 | Templates consume brittle happy-path-only services
SB07 | Template, policy, and seed parity, deterministic managed seed behavior, no fallback | repeated parsing, file I/O, JSON options, hardcoded fallback search, repeated policy compilation | duplicate key, raw secret, missing allowedTools, invalid policy selector, broken assignment | SB08 | MAF reconnects to unstable template/seed/policy behavior
SB09 | MAF adapters are thin, diagnosable, cleanup-safe, performance-reviewed, and have no hidden filters | codeanalytics/static cycles, large MAF files, dispatch hot paths, attach-time suppression scan | missing implementation, tool timeout, MCP list failure, denied required capability, cleanup failure | SB10/SB11 | UI/API builds on coupled runtime and generic errors

## Performance Review
Codeanalytics And Performance Review | Codeanalytics And Performance Review | Codeanalytics And Performance Review | Codeanalytics And Performance Review
Scoped evidence captured during bundle review. Counts are not direct defects, but they define checkpoint review pressure. | Scoped evidence captured during bundle review. Counts are not direct defects, but they define checkpoint review pressure. | Scoped evidence captured during bundle review. Counts are not direct defects, but they define checkpoint review pressure. | Scoped evidence captured during bundle review. Counts are not direct defects, but they define checkpoint review pressure.
Evidence | Value | Interpretation | Checkpoint Use
Snapshot | snap-20260628122504-1aa0230f | Scoped architecture snapshot for MAF/Core/Persistence/Tooling/Web/Tools | SB05/SB09
Capability DI seam | Only ICapabilityProofService surfaced in codeanalytics service search | Access decisions are not yet a dedicated reusable DI service | SB01/SB05/SB08
MAF type cycle | Reported by codeanalytics | Runtime capability code already has cycle pressure | SB09 must not move or worsen it
MAF project refs | Core, Tooling, Tools.Documents | MAF is still capability composition hub | SB08 adapter-only rule
LINQ chain candidates | 832 | Manual review needed in runtime/dispatch/materialization hot paths | SB05/SB09 performance scan
new List candidates | 63 | Pre-size materialized descriptors and avoid repeated allocation | SB05/SB07
new Dictionary candidates | 45 | Use ordinal comparers and static/read-only lookups where appropriate | SB05/SB07
new JsonSerializerOptions | 7 | Cache options or use source-gen contexts in new template/setup flows | SB05/SB07/SB09
Policy parsing | New risk | Compile template/UI policy text once to typed selectors; do not parse per tool call | SB05/SB07/SB09
Task.Result/.Wait candidates | 8 | Manual async review required around touched code | SB05/SB09
Largest scoped MAF file | MafAgentRuntime.cs: 2418 lines | Reconnection must not add more orchestration here | SB08/SB09
Seed builder size | SandboxWorkspaceSeedBuilder.cs: 1131 lines | Template materialization should reduce seed hardcoding | SB06/SB07

## Naming Standards
Naming Standards | Naming Standards | Naming Standards | Naming Standards | Naming Standards
Compatibility-oriented conventions based on current repo behavior plus MCP/OpenAI/Anthropic-compatible tool naming. | Compatibility-oriented conventions based on current repo behavior plus MCP/OpenAI/Anthropic-compatible tool naming. | Compatibility-oriented conventions based on current repo behavior plus MCP/OpenAI/Anthropic-compatible tool naming. | Compatibility-oriented conventions based on current repo behavior plus MCP/OpenAI/Anthropic-compatible tool naming. | Compatibility-oriented conventions based on current repo behavior plus MCP/OpenAI/Anthropic-compatible tool naming.
Concept | Convention | Example | Reason | Validator Owner
Capability key | lower kebab-case | workspace-dotnet-build | Matches existing agent skills.json assignments | SB01
Runtime tool name | lower snake_case | workspace_dotnet_build | Preserves current tool names and AI tool examples | SB01/SB02
MCP server key | lower kebab-case | playwright-local-mcp | Catalog identity, not function name | SB01/SB04
MCP tool name | server-provided, ASCII-compatible | browser_click | MCP names are server-owned; validate, do not invent | SB04
Operation key | typed value from template/UI text | run-validation | Compatibility bridge for process AllowedOperations | SB01/SB06
Capability tag | lower kebab-case typed value | mutation | Policy grouping without hardcoded string switches | SB01/SB05
Skill folder/key | lower kebab-case | aspnet-core-skill | Filesystem-readable and compatible with explicit skill invocation | SB03
C# constants | generated or strongly typed wrappers | ToolNames.WorkspaceDotNetBuild | No magic strings in runtime logic | SB01/SB12

## Risk Gates
Risks And Reopen Gates | Risks And Reopen Gates | Risks And Reopen Gates | Risks And Reopen Gates | Risks And Reopen Gates | Risks And Reopen Gates
Critical migration risks and the gates that must stop downstream work. | Critical migration risks and the gates that must stop downstream work. | Critical migration risks and the gates that must stop downstream work. | Critical migration risks and the gates that must stop downstream work. | Critical migration risks and the gates that must stop downstream work. | Critical migration risks and the gates that must stop downstream work.
Risk | Severity | Trigger | Mitigation | Reopen Gate | Owner
Capability keys drift | High | Agent skills.json missing capability | Parity tests and typed constants | Reopen SB01/SB06/SB07 | Architecture
Runtime tool names drift | High | Policy or process tests fail | Preserve names and explicit aliases only | Reopen SB02/SB08 | Delivery
Silent hardcoded fallback | High | Template load failure still seeds catalog | Fail fast and add negative tests | Reopen SB06/SB07/SB12 | QA
External command execution unsafe | High | No timeout/schema/approval/bindings | Bounded invoker contracts | Reopen SB02/SB10 | Security
MCP process leak | High | Fake MCP still running after test | Lifecycle manager cleanup proof | Reopen SB04/SB09 | Runtime
Generic setup errors | High | UI/API shows only Error on MCP start | Structured categories and repair hints | Reopen SB01/SB04/SB10 | QA
Stringly restrictions | High | Runtime compares raw selector strings or operation names | Typed value objects and access policy converters | Reopen SB01/SB05/SB09 | Architecture
Hidden suppression | High | MAF hides skills/tools/MCPs after effective set evaluation | Single shared evaluator and suppression diagnostics | Reopen SB08/SB09 | Runtime
Policy grants missing capability | High | Allow rule exposes unassigned tool/skill/MCP | Candidate-set invariant and unit tests | Reopen SB01/SB05 | Security
UI setup hides errors | Medium | Save succeeds after failed setup test | Typed result states and component tests | Reopen SB10 | UX/QA
Regression proof too narrow | High | Only unit tests run | Unit/integration/component/e2e matrix | Reopen SB11 | QA
Old code remains active | Medium | Static search finds live hardcoded path | Guard tests and docs | Reopen SB12 | Architecture