## Summary
WebGL process workbench concept bundle
Execution-complete workbook for the Blazor + WebGL / 2.5D concept branch. Counts below are formula-driven and update from the detail sheets.
Bundle overview
Bundle name | webgl_process_workbench_concept_bundle
Prepared on | 2026-04-20
Execution stage | Completed
Concept direction | Thin Blazor wrapper + JS-owned WebGL runtime + constrained 2.5D scene
Preferred engine | Three.js runtime wrapper inside a universal Blazor component library
Workbook path | spreadsheets/01-user-stories-and-functional-matrix.xlsx
Formula-driven counts
Inputs
Requirements
Actors
User stories
Features
Templates
Scenarios
Main subbundles
Corrective playbooks
Representative templates
Template | Scale | Why selected | Source | Expected proof | Notes
customer-onboarding | Simple | Fast sanity check for sparse scenes. | Templates/Processes/manifest.json | Screenshot + semantic interaction proof | Use in sandbox switching and gate reviews
architecture-decision-governance | Medium | Branching plus governance semantics without maximum density. | Templates/Processes/manifest.json | Screenshot + semantic interaction proof | Use in sandbox switching and gate reviews
branching-code-review | Dense | Stress case for overlap, routing, and authoring. | Templates/Processes/manifest.json | Screenshot + semantic interaction proof | Use in sandbox switching and gate reviews
Architecture references
Source | URL | Why it matters | Bundle use
Blazor JS interop performance best practices | https://learn.microsoft.com/en-us/aspnet/core/blazor/performance/javascript-interoperability?view=aspnetcore-10.0 | Interop has overhead; avoid fine-grained or per-frame .NET ↔ JS calls. | Justifies JS-owned render loop.
Call JavaScript from .NET in Blazor | https://learn.microsoft.com/en-us/aspnet/core/blazor/javascript-interoperability/call-javascript-from-dotnet?view=aspnetcore-10.0 | Prerendering and network realities reinforce a strict browser boundary. | Supports resilient interop rules.
JavaScript location in Blazor apps | https://learn.microsoft.com/en-us/aspnet/core/blazor/javascript-interoperability/location-of-javascript?view=aspnetcore-10.0 | RCL static asset patterns and disposal guidance matter for the component library. | Supports asset-loading and disposal design.
Three.js renderer documentation | https://threejs.org/docs/pages/Renderer.html | Render loop and animation primitives live cleanly in JS. | Supports the initial concept engine choice.
Note on B8: This concept direction is the default prepared recommendation and should only be revisited through Gate A.

## Inputs
Normalized inputs
User request decomposed into granular bundle inputs and expected evidence.
Input ID | Input | Expected evidence | Bundle source
IN-01 | Prepare a detailed execution bundle and deliver it as a zip artifact. | bundle structure + zip presence | inputs/00-original-request.md
IN-02 | Mirror the repository's existing bundle and subbundle conventions instead of inventing a new format. | bundle layout consistency | inputs/00-original-request.md
IN-03 | Decide the best practical style for using WebGL in Blazor for process-diagram exploration. | explicit architecture decision | inputs/00-original-request.md
IN-04 | Current process diagrams are hard to read in 2D and the concept should test whether a 3D or 2.5D approach improves legibility. | readability review notes + screenshots | inputs/00-original-request.md
IN-05 | Phase 1 must add a component library that wraps WebGL with a basic rendering and interaction system comparable to the current canvas workbench. | new WebGL library skeleton + typed contracts | inputs/00-original-request.md
IN-06 | The WebGL library must stay universal and reusable outside the Processes module. | no process reference from library | inputs/00-original-request.md
IN-07 | Codex must then add a new sandbox project dedicated to the WebGL concept. | new sandbox project in solution | inputs/00-original-request.md
IN-08 | The sandbox must display a selected template process taken from the current process-template pack. | template-backed sandbox scene | inputs/00-original-request.md
IN-09 | The sandbox should allow switching between templates. | template selector + route/query state | inputs/00-original-request.md
IN-10 | The sandbox must support manipulation, including moving a node and changing a connection. | interactive in-memory editing | inputs/00-original-request.md
IN-11 | The work happens on a separate concept branch and should avoid destabilizing the production 2D process workspace. | production workspace left untouched | inputs/00-original-request.md
IN-12 | Codex must validate through screenshots because Playwright MCP cannot easily drive canvas or WebGL directly. | browser proof playbook + screenshot review | inputs/00-original-request.md
IN-13 | The base library should expose an interface or contract that lets Playwright MCP test semantic WebGL actions such as moving nodes. | automation bridge contract | inputs/00-original-request.md
IN-14 | The bundle should include an XLSX workbook covering user stories, features, and traceability. | xlsx workbook present | inputs/00-original-request.md
IN-15 | Subbundles must be phase-based and must force architecture reviews between phases. | review gates + stop rules | inputs/00-original-request.md
IN-16 | The bundle should include emergency/corrective subbundles that repair or refactor the concept before downstream work continues. | corrective playbooks | inputs/00-original-request.md
IN-17 | The current Process module and current 2D canvas implementation are the structural reference for IDs, semantics, and interaction patterns. | contract reuse notes | inputs/00-original-request.md
IN-18 | The concept should be able to compare multiple template complexities rather than a single trivial example. | simple/medium/dense template set | inputs/00-original-request.md
IN-19 | Codex should be able to validate actual state changes even when pixel-only validation would be weak. | semantic snapshot proof | inputs/00-original-request.md
IN-20 | The final result for this task is the prepared bundle itself, not implementation code in the repository. | prepared-only execution report | inputs/00-original-request.md

## Requirements
Normalized requirements
Execution-grade requirements derived from the request and repo audit.
Requirement ID | Domain | Requirement | Acceptance signal | Source inputs | Owning subbundle
RQ-01 | Bundle | Preserve the original request, source-artifact inventory, and structured summary inside the bundle. | Bundle contains `inputs/00-original-request.md`, `inputs/01-source-artifacts.md`, and `inputs/02-structured-input.md`. | IN-01, IN-02, IN-20 | 01-baseline-and-renderer-decision-lock
RQ-02 | Bundle | Ship an execution-grade initiative bundle with subbundles, codex instructions, proof contracts, reviews, and corrective playbooks. | Bundle layout matches initiative conventions and passes the prepared-stage validator. | IN-01, IN-02, IN-15, IN-16 | 01-baseline-and-renderer-decision-lock
RQ-03 | Architecture | Make an explicit technology decision for how WebGL should be used from Blazor in this repository. | Target-solution docs name the rendering boundary, engine choice, and non-goals. | IN-03, IN-04 | 01-baseline-and-renderer-decision-lock
RQ-04 | Architecture | Keep high-frequency rendering, camera control, hit-testing, drag preview, and connection preview inside JavaScript rather than inside Blazor render loops. | Architecture rules ban per-frame C# rendering or server round trips during pointer movement. | IN-03, IN-05, IN-11 | 03-threejs-runtime-foundation-and-host-component
RQ-05 | Library | Create the concept around a universal RCL named `CanDoItAll.Components.WebGlLib` or equivalent, with no reference to `CanDoItAll.Modules.Processes`. | New library compiles independently and only exposes generic contracts. | IN-05, IN-06 | 02-universal-webgl-library-skeleton-and-typed-contracts
RQ-06 | Library | Expose a typed scene contract and component surface analogous in spirit to `CanvasWorkbench`, but not coupled to process-specific node kinds. | Library defines scene, node, edge, camera, UI-state, diagnostics, and event DTOs. | IN-05, IN-06, IN-17 | 02-universal-webgl-library-skeleton-and-typed-contracts
RQ-07 | Library | Support baseline workbench controls: fit view, focus node, zoom, pan/orbit, selection, diagnostics, and export. | Runtime API and component surface include these controls with typed options. | IN-05, IN-13 | 03-threejs-runtime-foundation-and-host-component
RQ-08 | Library | Support authoring semantics needed by the concept: move node, connect/disconnect nodes, and surface change events back to .NET. | Runtime emits semantic events and sandbox can update its in-memory model. | IN-10, IN-13 | 07-authoring-interactions-and-in-memory-edit-model
RQ-09 | Scene design | Use a constrained 2.5D process scene rather than unrestricted free-form 3D as the default authoring mode. | Architecture docs define deterministic X/Y layout with limited semantic Z-depth and orthographic default camera. | IN-03, IN-04 | 05-process-template-projection-and-2_5d-scene-adapter
RQ-10 | Labels and automation | Keep labels crisp and automation-friendly through a DOM mirror or overlay layer instead of relying only on textured 3D text. | Library includes a label/accessibility/automation mirror layer with stable IDs and coordinates. | IN-12, IN-13, IN-19 | 03-threejs-runtime-foundation-and-host-component
RQ-11 | Sandbox | Add a new dedicated sandbox project to the solution for the WebGL concept rather than only extending the existing Canvas sandbox page. | Solution includes a dedicated sandbox project with its own routes and startup. | IN-07 | 06-dedicated-webgl-sandbox-and-template-switching
RQ-12 | Sandbox | Load real process templates from the existing template pack through the current template services instead of inventing fake process data. | Sandbox uses current template pack + projection services and can show at least three representative templates. | IN-08, IN-17, IN-18 | 05-process-template-projection-and-2_5d-scene-adapter
RQ-13 | Sandbox | Allow switching between template scenarios and camera/view presets inside the sandbox. | UI contains template selector and view/camera controls with deterministic state. | IN-09, IN-18 | 06-dedicated-webgl-sandbox-and-template-switching
RQ-14 | Sandbox | Keep the concept's edits in-memory only; do not persist or mutate the production process workspace as part of this branch concept. | No production persistence or `ProcessWorkspace` replacement is required in the concept sandbox. | IN-10, IN-11 | 07-authoring-interactions-and-in-memory-edit-model
RQ-15 | Automation | Expose a deterministic automation bridge that Playwright/MCP can call semantically, including scene snapshots, node coordinates, drag simulation, and connection simulation. | Runtime exposes global automation methods and a debug state object analogous to the current canvas runtime. | IN-12, IN-13, IN-19 | 09-automation-bridge-and-proof-surface
RQ-16 | Proof | Require screenshot proof plus semantic snapshot assertions; screenshots alone are not enough for authoring changes. | Proof contract includes both screenshot capture and semantic assertions for node move/connect flows. | IN-12, IN-19 | 09-automation-bridge-and-proof-surface
RQ-17 | Governance | Split the work into phase-based subbundles with explicit architecture review gates and no downstream progress on weak proof. | Plan includes Gate A, Gate B, and final closure gates with go/no-go decisions. | IN-15, IN-16 | 04-architecture-review-gate-a
RQ-18 | Governance | Provide corrective subbundles that reset renderer boundaries, scene contract/layout, or proof strategy before later phases continue. | Corrective playbooks are present and referenced by failure paths. | IN-16 | _corrective-renderer-boundary-reset
RQ-19 | Reference reuse | Reuse existing process IDs, branching semantics, and connection categories where possible so the concept remains relatable to the current 2D workbench. | Process adapter reuses template projection services and `ProcessCanvasCatalog` semantics. | IN-17 | 05-process-template-projection-and-2_5d-scene-adapter
RQ-20 | Validation | Define targeted build, component-test, and Playwright proof commands for the concept branch. | Bundle contains `codex/VALIDATION_COMMANDS.md` and proof docs with exact commands. | IN-12, IN-15 | 10-final-proof-closure-and-migration-guidance
RQ-21 | Workbook | Provide an XLSX workbook that tracks inputs, actors, requirements, user stories, features, scenarios, subbundles, and traceability. | Workbook exists in `spreadsheets/` and is referenced by requirements and traceability docs. | IN-14 | 01-baseline-and-renderer-decision-lock
RQ-22 | Asset strategy | Keep the new JS/WebGL asset pipeline isolated and deterministic, with no CDN dependency in the concept. | Library uses committed static assets and an explicit build path under repository tooling. | IN-05, IN-11 | 02-universal-webgl-library-skeleton-and-typed-contracts
RQ-23 | Migration | Close the bundle with a migration/pilot rubric that states when the concept is good enough to move toward the real process workspace. | Final guidance document defines pilot-entry criteria, out-of-scope items, and rollback triggers. | IN-04, IN-11, IN-20 | 10-final-proof-closure-and-migration-guidance

## Actors
Actors and roles
Human and agent roles that shape execution, proof, and review.
Actor ID | Actor | Type | Responsibility | Scope
ACT-01 | Platform / solution architect | Human | Owns the concept decision, reviews readability and architecture gates. | Bundle, Architecture, Reviews
ACT-02 | Codex implementation agent | AI | Executes the subbundles in order, captures proof, and respects stop rules. | All execution phases
ACT-03 | Process designer | Human | Explores template processes in the sandbox and evaluates whether 2.5D improves comprehension. | Sandbox, Templates
ACT-04 | Blazor host shell | System | Hosts the RCL component and dispatches coarse-grained semantic events into .NET. | WebGlLib, Sandbox
ACT-05 | WebGL runtime | System | Owns rendering, hit-testing, camera updates, drag previews, and automation snapshots in JavaScript. | WebGlLib JS runtime
ACT-06 | Playwright / MCP harness | System | Runs screenshot capture and semantic automation-bridge assertions. | Tests, Proof

## UserStories
User stories
Stories Codex should satisfy through the staged concept work.
Story ID | Theme | Actor ID | Story | Acceptance | Priority | Area | Source inputs | Owning subbundle
US-01 | Library foundation | ACT-01 | As the solution architect I want the WebGL concept isolated in a universal component library so later modules can reuse it without inheriting process-specific baggage. | The library references BaseLib/Common only and exposes generic scene contracts. | High | WebGlLib, Solution | IN-05, IN-06 | 02-universal-webgl-library-skeleton-and-typed-contracts
US-02 | Rendering boundary | ACT-01 | As the architect I want rendering and hit-testing kept in JavaScript so Blazor does not become the frame loop bottleneck. | Architecture docs and runtime implementation keep per-frame work in JS and .NET only receives coarse events. | High | Architecture, WebGlLib | IN-03, IN-05, IN-11 | 03-threejs-runtime-foundation-and-host-component
US-03 | Concept readability | ACT-03 | As a process designer I want to inspect a process in a 2.5D scene so I can judge whether depth reduces clutter compared with the current 2D view. | Sandbox offers overview and focused views with readable labels and screenshot proof. | High | Sandbox, Templates | IN-04, IN-08 | 06-dedicated-webgl-sandbox-and-template-switching
US-04 | Template switching | ACT-03 | As a designer I want to switch between simple, medium, and dense template processes to understand where the concept helps and where it fails. | Sandbox template selector loads representative templates without restarting the app. | High | Sandbox, Templates | IN-08, IN-09, IN-18 | 06-dedicated-webgl-sandbox-and-template-switching
US-05 | Camera presets | ACT-03 | As a reviewer I want orthographic, perspective, and focus presets so I can compare authoring readability modes. | Sandbox includes camera/view presets and the default is orthographic. | Medium | Sandbox, WebGlLib | IN-03, IN-04 | 06-dedicated-webgl-sandbox-and-template-switching
US-06 | Node move | ACT-03 | As a designer I want to drag a node and see the scene update immediately so the concept proves authoring is viable. | Dragging updates the in-memory scene and the last command summary reflects the move. | High | Sandbox, WebGlLib | IN-10 | 07-authoring-interactions-and-in-memory-edit-model
US-07 | Connection editing | ACT-03 | As a designer I want to create or remove a connection so the concept proves authoring is not view-only. | A semantic connect/disconnect flow exists and updates the in-memory model. | High | Sandbox, WebGlLib | IN-10 | 07-authoring-interactions-and-in-memory-edit-model
US-08 | Selection context | ACT-03 | As a designer I want selection and a lightweight inspector so I can understand what a node or edge represents in the scene. | Selecting a node highlights it and shows metadata/semantics in a side panel or floating panel. | Medium | Sandbox, WebGlLib | IN-10, IN-17 | 07-authoring-interactions-and-in-memory-edit-model
US-09 | Reset and reload | ACT-03 | As a reviewer I want to reset the current template to its original state so experiments remain repeatable. | Sandbox can reset the in-memory session back to the selected template projection. | Medium | Sandbox | IN-09, IN-10 | 07-authoring-interactions-and-in-memory-edit-model
US-10 | Semantic automation | ACT-06 | As the Playwright harness I want semantic helper methods such as scene snapshot, drag simulation, and connect simulation so I am not limited to brittle pixel-only interactions. | Runtime exposes stable global helpers and host state with deterministic node/port lookup. | High | WebGlLib, Playwright | IN-12, IN-13, IN-19 | 09-automation-bridge-and-proof-surface
US-11 | DOM mirror | ACT-06 | As the harness I want DOM mirror anchors for nodes and ports so I can inspect IDs and screen-space projections without parsing WebGL buffers. | DOM mirror layer exists with stable data attributes and accessibility labels. | High | WebGlLib, Playwright | IN-12, IN-13 | 09-automation-bridge-and-proof-surface
US-12 | Screenshot export | ACT-06 | As the harness I want the runtime to export scene screenshots directly so proof can be captured even when browser pointer automation is limited. | Runtime provides `exportImageData` or equivalent with deterministic output. | High | WebGlLib, Playwright | IN-12, IN-13 | 09-automation-bridge-and-proof-surface
US-13 | Concept isolation | ACT-01 | As the architect I want the concept to avoid changing `ProcessWorkspace` so I can evaluate WebGL without destabilizing the production editor. | No production process route replacement is required in the concept branch. | High | Processes, Sandbox | IN-11 | 01-baseline-and-renderer-decision-lock
US-14 | Review gates | ACT-02 | As Codex I want explicit architecture gates and stop rules so I never continue on a weak or wrong direction. | Bundle contains mandatory Gate A, Gate B, and final closure gate instructions. | High | Bundle, Reviews | IN-15, IN-16 | 04-architecture-review-gate-a
US-15 | Corrective playbooks | ACT-02 | As Codex I want ready corrective subbundles so I can repair architecture, layout, or proof problems before continuing. | Corrective subbundles exist and are wired into plan failure paths. | High | Bundle, Reviews | IN-16 | _corrective-renderer-boundary-reset
US-16 | Workbook traceability | ACT-01 | As the architect I want workbook-backed traceability so I can audit what Codex must implement and prove. | Workbook links stories/features to subbundles and proof expectations. | Medium | Workbook, Traceability | IN-14 | 01-baseline-and-renderer-decision-lock
US-17 | Migration rubric | ACT-01 | As the architect I want a migration rubric so I know when the concept is mature enough to try on the real Processes workspace. | Final guidance defines pilot entry criteria and rollback triggers. | Medium | Architecture, Reviews | IN-20 | 10-final-proof-closure-and-migration-guidance
US-18 | Asset determinism | ACT-02 | As Codex I want a deterministic asset strategy with committed build outputs so the concept can build and run on CI without remote dependencies. | JS runtime assets are committed and build steps are documented under repository tooling. | Medium | WebGlLib, Tooling | IN-05, IN-11 | 02-universal-webgl-library-skeleton-and-typed-contracts

## Features
Feature inventory
Functions and platform surfaces the concept is expected to deliver or prove.
Feature ID | Area | Feature | Description | Owning subbundle
FT-01 | Library | WebGlWorkbench component shell | Generic Blazor component that hosts the WebGL runtime and forwards typed scene updates. | 02-universal-webgl-library-skeleton-and-typed-contracts
FT-02 | Library | Typed scene contracts | Scene, node, edge, port, camera, UI-state, diagnostics, and event DTOs. | 02-universal-webgl-library-skeleton-and-typed-contracts
FT-03 | Library | Asset loader components | Head/body or module-loading helpers equivalent to the current CanvasLib asset pattern. | 02-universal-webgl-library-skeleton-and-typed-contracts
FT-04 | Runtime | Three.js scene host | Scene, renderer, camera, and lifecycle foundation behind a single global runtime entry point. | 03-threejs-runtime-foundation-and-host-component
FT-05 | Runtime | Orthographic default camera | Authoring camera that preserves scale and reduces perspective distortion. | 03-threejs-runtime-foundation-and-host-component
FT-06 | Runtime | Optional perspective preset | Secondary camera preset used only for exploration/review, not default authoring. | 06-dedicated-webgl-sandbox-and-template-switching
FT-07 | Runtime | 2.5D layer policy | Deterministic Z-depth rules for roles, steps, branch routers, labels, and links. | 05-process-template-projection-and-2_5d-scene-adapter
FT-08 | Runtime | HTML/DOM label overlay | Crisp labels rendered outside the WebGL text path. | 03-threejs-runtime-foundation-and-host-component
FT-09 | Runtime | Selection/highlight model | Scene selection state with visual emphasis and typed change events. | 07-authoring-interactions-and-in-memory-edit-model
FT-10 | Runtime | Node drag interaction | Pointer-driven drag with JS-owned preview and .NET commit on release. | 07-authoring-interactions-and-in-memory-edit-model
FT-11 | Runtime | Connect/disconnect interaction | Semantic edge authoring flow for create/remove or reroute actions. | 07-authoring-interactions-and-in-memory-edit-model
FT-12 | Runtime | Diagnostics snapshot | Metrics and debug diagnostics returned by the runtime for proof and troubleshooting. | 09-automation-bridge-and-proof-surface
FT-13 | Runtime | Scene snapshot | Serializable snapshot of visible nodes, edges, camera, and projected anchors. | 09-automation-bridge-and-proof-surface
FT-14 | Runtime | Screenshot export | Direct image-data export from the current scene for review artifacts. | 09-automation-bridge-and-proof-surface
FT-15 | Runtime | Automation drag helper | Semantic `simulateDrag` helper for deterministic movement tests. | 09-automation-bridge-and-proof-surface
FT-16 | Runtime | Automation connection helper | Semantic helper that can create or remove a connection without fragile raw pointer scripting. | 09-automation-bridge-and-proof-surface
FT-17 | Runtime | Finish interaction helper | Explicit interaction finalizer for tests and recovery. | 09-automation-bridge-and-proof-surface
FT-18 | Adapter | Process template projection adapter | Projection from real process templates to the generic WebGL scene contract. | 05-process-template-projection-and-2_5d-scene-adapter
FT-19 | Adapter | Connection-category mapping | Map process dependency, responsibility, messaging, and artifact semantics to visual styles. | 05-process-template-projection-and-2_5d-scene-adapter
FT-20 | Sandbox | Dedicated WebGL sandbox project | New project with its own routes and startup. | 06-dedicated-webgl-sandbox-and-template-switching
FT-21 | Sandbox | Template selector | Simple/medium/dense template switching inside the sandbox. | 06-dedicated-webgl-sandbox-and-template-switching
FT-22 | Sandbox | View preset controls | Overview, roles, dependencies, branching, and focus-selected presets. | 06-dedicated-webgl-sandbox-and-template-switching
FT-23 | Sandbox | In-memory edit store | State holder for the selected template, unsaved edits, and reset/reload actions. | 07-authoring-interactions-and-in-memory-edit-model
FT-24 | Sandbox | Inspector / event log | Human-readable panel showing selection and last command details. | 07-authoring-interactions-and-in-memory-edit-model
FT-25 | Sandbox | Deterministic test mode | Mode that disables camera easing/animation jitter for repeatable screenshots. | 09-automation-bridge-and-proof-surface
FT-26 | Governance | Architecture Gate A memo | Review that checks universal boundary and runtime choice after the foundation exists. | 04-architecture-review-gate-a
FT-27 | Governance | Architecture Gate B memo | Review that checks scene semantics, sandbox scope, and interaction value before proof finalization. | 08-architecture-review-gate-b
FT-28 | Governance | Corrective playbooks | Renderer-boundary, scene-layout, and automation-reset paths. | _corrective-renderer-boundary-reset
FT-29 | Governance | Validation commands | Exact build, component-test, and Playwright command set. | 10-final-proof-closure-and-migration-guidance
FT-30 | Governance | Migration rubric | Pilot-entry criteria and rollback triggers for moving beyond concept stage. | 10-final-proof-closure-and-migration-guidance

## Templates
Template candidate matrix
Real process templates available in the repository and their density characteristics.
Template | Steps | Branch steps | Dependencies | Artifacts | Density | Complexity score | Representative | Notes
branching-code-review | 13 | 1 | 16 | 13 | Dense |  | Yes | Stress case for overlap, routing, and authoring.
software-delivery | 9 | 0 | 17 | 11 | Dense |  | No
ai-assisted-change-delivery | 8 | 2 | 9 | 14 | Medium |  | No
hotfix-rollout | 7 | 0 | 7 | 7 | Simple |  | No
release-readiness-and-deployment | 7 | 1 | 6 | 12 | Medium |  | No
architecture-decision-governance | 6 | 1 | 5 | 9 | Medium |  | Yes | Branching plus governance semantics without maximum density.
oss-intake-supply-chain-governance | 6 | 1 | 5 | 11 | Medium |  | No
customer-onboarding | 3 | 0 | 2 | 3 | Simple |  | Yes | Fast sanity check for sparse scenes.
incident-response | 3 | 0 | 2 | 3 | Simple |  | No
Note on G5: Formula = Steps + (BranchSteps*2) + Dependencies + Artifacts

## Scenarios
Proof scenarios
Scenarios that should be validated during implementation and review gates.
Scenario ID | Category | Name | Description | Proof mode
SC-01 | Baseline | Minimal scene smoke | Prove the new WebGL library can host a generic scene with 3-5 nodes before process-specific projection begins. | Automated
SC-02 | Template | Simple template: customer-onboarding | Validate the concept on a small, low-branching process. | Automated + screenshot
SC-03 | Template | Medium template: architecture-decision-governance | Validate branching and governance semantics in a moderate scene. | Automated + screenshot
SC-04 | Template | Dense template: branching-code-review | Validate a denser authoring surface where edge clutter is a real issue. | Automated + screenshot
SC-05 | Camera | Overview camera preset | Show the whole scene with readable labels and no clipped content. | Screenshot
SC-06 | Interaction | Move a node | Use semantic drag helper and prove the node position changed in scene snapshot. | Automated + screenshot
SC-07 | Interaction | Create or remove a connection | Use semantic automation or sandbox UI to prove connection mutations work. | Automated + screenshot
SC-08 | Automation | Export screenshot image data | Verify the runtime can export a deterministic proof image. | Automated
SC-09 | Automation | DOM mirror lookup | Verify node and port anchors are discoverable with stable IDs. | Automated
SC-10 | Closure | Pilot readiness review | Decide whether the concept is strong enough for a future pilot on the real Processes workspace. | Manual review

## Subbundles
Subbundle plan
Main execution slices and corrective playbooks used to keep the concept architecture honest.
Key | Kind | Title | Purpose | Depends on | Corrective on failure | Validation command count | Readme path | Task path
01-baseline-and-renderer-decision-lock | Main | Baseline and renderer decision lock | Establish the current-process and current-canvas baseline, document the renderer strategy, and lock the concept boundaries before any implementation starts. |  | _corrective-renderer-boundary-reset | 1 | subbundles/01-baseline-and-renderer-decision-lock/README.md | subbundles/01-baseline-and-renderer-decision-lock/task.json
02-universal-webgl-library-skeleton-and-typed-contracts | Main | Universal WebGL library skeleton and typed contracts | Create the new universal WebGL RCL, wire it into the solution, and define generic scene and event contracts without any Processes dependency. | 01-baseline-and-renderer-decision-lock | _corrective-renderer-boundary-reset | 2 | subbundles/02-universal-webgl-library-skeleton-and-typed-contracts/README.md | subbundles/02-universal-webgl-library-skeleton-and-typed-contracts/task.json
03-threejs-runtime-foundation-and-host-component | Main | Three.js runtime foundation and host component | Implement the JS-owned WebGL runtime foundation, host-state lifecycle, label overlay shell, and the first interactive component wrapper for the new library. | 02-universal-webgl-library-skeleton-and-typed-contracts | _corrective-renderer-boundary-reset | 2 | subbundles/03-threejs-runtime-foundation-and-host-component/README.md | subbundles/03-threejs-runtime-foundation-and-host-component/task.json
04-architecture-review-gate-a | Main | Architecture review gate A | Review the new library and runtime foundation before any process-template projection or sandbox growth continues. | 03-threejs-runtime-foundation-and-host-component | _corrective-renderer-boundary-reset | 1 | subbundles/04-architecture-review-gate-a/README.md | subbundles/04-architecture-review-gate-a/task.json
05-process-template-projection-and-2_5d-scene-adapter | Main | Process template projection and 2.5D scene adapter | Build the process-specific adapter that projects real template processes into the generic WebGL scene while reusing the current process IDs, categories, and branching semantics. | 04-architecture-review-gate-a | _corrective-scene-contract-and-layout-reset | 2 | subbundles/05-process-template-projection-and-2_5d-scene-adapter/README.md | subbundles/05-process-template-projection-and-2_5d-scene-adapter/task.json
06-dedicated-webgl-sandbox-and-template-switching | Main | Dedicated WebGL sandbox and template switching | Add the dedicated WebGL sandbox project, surface the projected templates, and provide camera/view controls for human concept review. | 05-process-template-projection-and-2_5d-scene-adapter | _corrective-scene-contract-and-layout-reset | 2 | subbundles/06-dedicated-webgl-sandbox-and-template-switching/README.md | subbundles/06-dedicated-webgl-sandbox-and-template-switching/task.json
07-authoring-interactions-and-in-memory-edit-model | Main | Authoring interactions and in-memory edit model | Make the sandbox concept interactive through in-memory node movement, connection changes, selection/inspector context, and resettable command history. | 06-dedicated-webgl-sandbox-and-template-switching | _corrective-scene-contract-and-layout-reset | 1 | subbundles/07-authoring-interactions-and-in-memory-edit-model/README.md | subbundles/07-authoring-interactions-and-in-memory-edit-model/task.json
08-architecture-review-gate-b | Main | Architecture review gate B | Review the interactive sandbox concept before automation and final proof work proceeds. | 07-authoring-interactions-and-in-memory-edit-model | _corrective-scene-contract-and-layout-reset | 1 | subbundles/08-architecture-review-gate-b/README.md | subbundles/08-architecture-review-gate-b/task.json
09-automation-bridge-and-proof-surface | Main | Automation bridge and proof surface | Add the semantic automation bridge, host debug state, DOM mirror queries, export hooks, and Playwright tests needed to prove WebGL interactions deterministically. | 08-architecture-review-gate-b | _corrective-automation-and-proof-reset | 1 | subbundles/09-automation-bridge-and-proof-surface/README.md | subbundles/09-automation-bridge-and-proof-surface/task.json
10-final-proof-closure-and-migration-guidance | Main | Final proof, closure, and migration guidance | Close the concept with full proof, final review notes, workbook completion, and a migration rubric for any future pilot on the real Processes workspace. | 09-automation-bridge-and-proof-surface | _corrective-automation-and-proof-reset | 3 | subbundles/10-final-proof-closure-and-migration-guidance/README.md | subbundles/10-final-proof-closure-and-migration-guidance/task.json
_corrective-renderer-boundary-reset | Corrective | Corrective renderer-boundary reset | Repair any failure where the new WebGL library stopped being universal, the runtime boundary drifted into Blazor/server round trips, or the JS/asset strategy became unstable. |  |  | 1 | subbundles/_corrective-renderer-boundary-reset/README.md | subbundles/_corrective-renderer-boundary-reset/task.json
_corrective-scene-contract-and-layout-reset | Corrective | Corrective scene-contract and layout reset | Repair failures where the projected process scene became visually confusing, semantically inconsistent with current process IDs/categories, or too coupled to the sandbox. |  |  | 1 | subbundles/_corrective-scene-contract-and-layout-reset/README.md | subbundles/_corrective-scene-contract-and-layout-reset/task.json
_corrective-automation-and-proof-reset | Corrective | Corrective automation and proof reset | Repair failures where screenshots were non-deterministic, semantic automation was too weak, or final proof could not verify actual WebGL state changes. |  |  | 1 | subbundles/_corrective-automation-and-proof-reset/README.md | subbundles/_corrective-automation-and-proof-reset/task.json

## Traceability
Input traceability
Cross-map from raw inputs to requirements, stories, subbundles, and proof expectations.
Input ID | Requirements | Stories | Subbundles | Proof signal
IN-01 | RQ-01, RQ-02 |  |  | bundle structure + zip presence
IN-02 | RQ-01, RQ-02 |  |  | bundle layout consistency
IN-03 | RQ-03, RQ-04, RQ-09 | US-02, US-05 | 03-threejs-runtime-foundation-and-host-component, 06-dedicated-webgl-sandbox-and-template-switching | explicit architecture decision
IN-04 | RQ-03, RQ-09, RQ-23 | US-03, US-05 | 06-dedicated-webgl-sandbox-and-template-switching | readability review notes + screenshots
IN-05 | RQ-04, RQ-05, RQ-06, RQ-07, RQ-22 | US-01, US-02, US-18 | 02-universal-webgl-library-skeleton-and-typed-contracts, 03-threejs-runtime-foundation-and-host-component | new WebGL library skeleton + typed contracts
IN-06 | RQ-05, RQ-06 | US-01 | 02-universal-webgl-library-skeleton-and-typed-contracts | no process reference from library
IN-07 | RQ-11 |  |  | new sandbox project in solution
IN-08 | RQ-12 | US-03, US-04 | 06-dedicated-webgl-sandbox-and-template-switching | template-backed sandbox scene
IN-09 | RQ-13 | US-04, US-09 | 06-dedicated-webgl-sandbox-and-template-switching, 07-authoring-interactions-and-in-memory-edit-model | template selector + route/query state
IN-10 | RQ-08, RQ-14 | US-06, US-07, US-08, US-09 | 07-authoring-interactions-and-in-memory-edit-model | interactive in-memory editing
IN-11 | RQ-04, RQ-14, RQ-22, RQ-23 | US-02, US-13, US-18 | 01-baseline-and-renderer-decision-lock, 02-universal-webgl-library-skeleton-and-typed-contracts, 03-threejs-runtime-foundation-and-host-component | production workspace left untouched
IN-12 | RQ-10, RQ-15, RQ-16, RQ-20 | US-10, US-11, US-12 | 09-automation-bridge-and-proof-surface | browser proof playbook + screenshot review
IN-13 | RQ-07, RQ-08, RQ-10, RQ-15 | US-10, US-11, US-12 | 09-automation-bridge-and-proof-surface | automation bridge contract
IN-14 | RQ-21 | US-16 | 01-baseline-and-renderer-decision-lock | xlsx workbook present
IN-15 | RQ-02, RQ-17, RQ-20 | US-14 | 04-architecture-review-gate-a | review gates + stop rules
IN-16 | RQ-02, RQ-17, RQ-18 | US-14, US-15 | 04-architecture-review-gate-a, _corrective-renderer-boundary-reset | corrective playbooks
IN-17 | RQ-06, RQ-12, RQ-19 | US-08 | 07-authoring-interactions-and-in-memory-edit-model | contract reuse notes
IN-18 | RQ-12, RQ-13 | US-04 | 06-dedicated-webgl-sandbox-and-template-switching | simple/medium/dense template set
IN-19 | RQ-10, RQ-15, RQ-16 | US-10 | 09-automation-bridge-and-proof-surface | semantic snapshot proof
IN-20 | RQ-01, RQ-23 | US-17 | 10-final-proof-closure-and-migration-guidance | completed execution report + closure review

## Hotspots
Repository hotspots
Long or central files that should be treated cautiously during implementation.
Path | Lines | Area | Execution note
tests/CanDoItAll.Tests.Playwright/AppSmokeTests.cs | 5106 | Playwright | High-complexity file; touch narrowly and prefer surgical changes.
tests/CanDoItAll.Tests.Components/ProcessWorkspaceTests.cs | 1459 | Component tests | High-complexity file; touch narrowly and prefer surgical changes.
src/CanDoItAll.Components.CanvasLib/Components/Workbench/CanvasWorkbench.razor | 943 | UI component | High-complexity file; touch narrowly and prefer surgical changes.
src/CanDoItAll.Components.CanvasLib/wwwroot/js/runtime/workbench/07a-runtime-interaction-router.js | 899 | Runtime JS | High-complexity file; touch narrowly and prefer surgical changes.
src/CanDoItAll.Components.CanvasLib/wwwroot/js/runtime/workbench/07-runtime-entry.js | 868 | Runtime JS | High-complexity file; touch narrowly and prefer surgical changes.
src/CanDoItAll.Components.CanvasLib/wwwroot/js/runtime/workbench/07b-runtime-rendering.js | 578 | Runtime JS | High-complexity file; touch narrowly and prefer surgical changes.
src/CanDoItAll.Modules.Processes/Components/ProcessWorkspace.Canvas.Persistence.cs | 520 | UI component | High-complexity file; touch narrowly and prefer surgical changes.
src/CanDoItAll.Modules.Processes/Components/ProcessWorkspace.Canvas.Links.cs | 512 | UI component | High-complexity file; touch narrowly and prefer surgical changes.
tests/CanDoItAll.Tests.Components/ProcessCanvasSurfaceFactoryTests.cs | 495 | Component tests | High-complexity file; touch narrowly and prefer surgical changes.
src/CanDoItAll.Modules.Processes/ProcessCanvasSurfaceFactory.cs | 488 | UI component | High-complexity file; touch narrowly and prefer surgical changes.
src/CanDoItAll.Modules.Processes/ProcessCanvasCatalog.cs | 486 | UI component | High-complexity file; touch narrowly and prefer surgical changes.
src/CanDoItAll.Modules.Processes/Components/ProcessWorkspace.razor | 447 | UI component | High-complexity file; touch narrowly and prefer surgical changes.
src/CanDoItAll.Modules.Processes/Components/ProcessWorkspace.Canvas.Actions.cs | 409 | UI component | High-complexity file; touch narrowly and prefer surgical changes.
src/CanDoItAll.Modules.Processes/ProcessCanvasSurfaceFactory.Ports.cs | 378 | UI component | High-complexity file; touch narrowly and prefer surgical changes.
src/CanDoItAll.Modules.Processes/ProcessCanvasBranching.cs | 374 | UI component | High-complexity file; touch narrowly and prefer surgical changes.
src/CanDoItAll.Modules.Processes/Components/ProcessWorkspace.Canvas.cs | 332 | UI component | High-complexity file; touch narrowly and prefer surgical changes.
src/CanDoItAll.Modules.Processes/ProcessCanvasSurfaceFactory.Chrome.cs | 273 | UI component | High-complexity file; touch narrowly and prefer surgical changes.
src/CanDoItAll.Modules.Processes/ProcessDefinitionEditorModels.cs | 253 | UI component | High-complexity file; touch narrowly and prefer surgical changes.
src/CanDoItAll.Modules.Processes/Components/ProcessWorkspace.razor.cs | 247 | UI component | High-complexity file; touch narrowly and prefer surgical changes.
src/CanDoItAll.Components.Sandbox/Components/Pages/Canvas.razor | 230 | UI component | High-complexity file; touch narrowly and prefer surgical changes.
src/CanDoItAll.Modules.Processes/ProcessCanvasSurfaceFactory.Links.cs | 213 | UI component | High-complexity file; touch narrowly and prefer surgical changes.
src/CanDoItAll.Components.CanvasLib/Canvas/Workbench/CanvasWorkbenchUiState.cs | 185 | UI component | High-complexity file; touch narrowly and prefer surgical changes.
src/CanDoItAll.Components.CanvasLib/Canvas/Workbench/CanvasWorkbenchNode.cs | 151 | UI component | High-complexity file; touch narrowly and prefer surgical changes.
src/CanDoItAll.Components.CanvasLib/Canvas/Workbench/CanvasWorkbenchEvents.cs | 49 | UI component | High-complexity file; touch narrowly and prefer surgical changes.
src/CanDoItAll.Components.CanvasLib/Canvas/Workbench/CanvasWorkbenchSurface.cs | 33 | UI component | High-complexity file; touch narrowly and prefer surgical changes.
src/CanDoItAll.Components.Sandbox/Program.cs | 21 | UI component | High-complexity file; touch narrowly and prefer surgical changes.

## Research
External research references
Public documentation referenced by the architecture notes and summary sheet.
Source | URL | Note | Why used
Blazor JS interop performance best practices | https://learn.microsoft.com/en-us/aspnet/core/blazor/performance/javascript-interoperability?view=aspnetcore-10.0 | Interop has overhead; avoid fine-grained or per-frame .NET ↔ JS calls. | Justifies JS-owned render loop.
Call JavaScript from .NET in Blazor | https://learn.microsoft.com/en-us/aspnet/core/blazor/javascript-interoperability/call-javascript-from-dotnet?view=aspnetcore-10.0 | Prerendering and network realities reinforce a strict browser boundary. | Supports resilient interop rules.
JavaScript location in Blazor apps | https://learn.microsoft.com/en-us/aspnet/core/blazor/javascript-interoperability/location-of-javascript?view=aspnetcore-10.0 | RCL static asset patterns and disposal guidance matter for the component library. | Supports asset-loading and disposal design.
Three.js renderer documentation | https://threejs.org/docs/pages/Renderer.html | Render loop and animation primitives live cleanly in JS. | Supports the initial concept engine choice.