## Summary
Field | Value | Proof
Bundle | providers-processes-merge-readiness | codex/bundles/providers-processes-merge-readiness
Execution state | Executed | reviews/01-execution-report.md
Closure decision | Completed-stage bundle valid with broad-suite caveats | reviews/02-readiness-validation.md
Final build | Passed | proof/SB06/transcripts/solution-build-after-final-edits-slnx.txt
Completed validator | Passed | proof/SB06/transcripts/bundle-validator-completed-after-execution.txt
5032 instance | HTTP 200 on loopback port 5032 | proof/SB04/transcripts/web-5032-start.out.log
Browser proof | Focused process-shell smoke passed; broad Playwright debt remains | proof/SB04/transcripts/playwright-process-shell-final-navigation-smoke.txt
Documentation | Provider project READMEs added and asserted | proof/SB05/transcripts/readme-coverage-assertions.txt

## Implementation
Area | Files | Outcome
Provider dispatch and tests | src/CanDoItAll.AgentFramework.Models/Providers/ProviderDispatchModels.cs; tests/CanDoItAll.Tests.Unit/AgentFramework/Providers/ProviderRuntimeImageGenerationServiceTests.cs | Timeout/in-flight limits and safer provider tests.
Provider seed fallback repair | src/CanDoItAll.AgentFramework.Models/Providers/Seeds/ManagedSeedProviderFallbacks.cs; src/CanDoItAll.AgentFramework.Persistence/Seeds/SandboxWorkspaceSeedNormalizer.cs | Managed fallback providers are recognized during catalog repair without preserving generated fallback assignments as explicit user choices.
Unknown provider connector persistence | src/CanDoItAll.Modules.Workspace/Models/WorkspaceModels.cs | Unknown provider plugins keep posted pricing/private settings instead of being forced into known pricing kinds.
Process projection boundary | src/CanDoItAll.Processes.Projections/*; src/CanDoItAll.Processes.Persistence/CanDoItAll.Processes.Persistence.csproj | Persistence no longer references Processes.Application for projection read contracts.
Process canvas hardening | src/CanDoItAll.Processes.Application/ProcessDefinitionCanvasEditorProjectionService.cs; src/CanDoItAll.Modules.Processes/Components/ProcessDefinitionCanvasPanel.razor | Stale recompose applies to the current projection; stale mutating commands still reject.
Shared button hardening | src/CanDoItAll.AppComponents/Components/Button.razor | Click callbacks are guarded against re-entry while in flight.
Runtime plugin workflow descriptor | src/CanDoItAll.Modules.Plugins/Catalog/PluginPackageServices.cs | Runtime plugin workflow executors register descriptor sources.
Migration/query-plan repair | src/CanDoItAll.Composition/RuntimeHostServiceCollectionExtensions.cs; tests/CanDoItAll.Tests.Integration/PostgreSqlClaimQueryPlanIntegrationTests.cs | Current PostgreSQL migrations and V3 process tables/indexes are asserted.
Documentation | src/CanDoItAll.AgentFramework.Providers/README.md; src/CanDoItAll.AgentFramework.ProviderPipelines/README.md | New provider projects have merge-ready README coverage.

## Tests
Gate | Status | Transcript
Provider focused tests | Pass | proof/SB01/transcripts/provider-focused-tests-after-reflection-fix.txt
Process focused unit tests | Pass | proof/SB02/transcripts/process-focused-unit-tests.txt
Process canvas version contract | Pass | proof/SB02/transcripts/process-canvas-version-contract-tests-after-final-edits.txt
Unit suite after integration fixes | Pass | proof/SB03/transcripts/unit-tests-final-after-integration-fixes.txt
Process shell component class | Pass | proof/SB03/transcripts/component-process-workspace-shell-after-final-edits.txt
Targeted integration chunks/classes | Pass | proof/SB03/transcripts/integration-*.txt
Focused process-shell Playwright | Pass | proof/SB04/transcripts/playwright-process-shell-final-navigation-smoke.txt
Full solution build | Pass | proof/SB06/transcripts/solution-build-after-final-edits-slnx.txt
Completed-stage bundle validator | Pass | proof/SB06/transcripts/bundle-validator-completed-after-execution.txt

## Caveats
Caveat | Status | Follow-up
Full integration/component broad runners can hang in this workspace. | Documented | Use successful class/chunk transcripts as current proof; stabilize broad runners separately.
Full Playwright includes known quarantined/generated/CRM flows. | Documented | Keep quarantine policy aligned and repair flows individually.
Category!=Quarantined still exposes unrelated legacy UI smoke failures. | Open | Separate UI-test stabilization pass for project-structure overlay and shell chrome assertions.
Live provider tests are environment dependent. | Documented | Retain external/live transcripts and separate credential blockers from source correctness.

## Commands
Command | Result | Transcript
dotnet test tests/CanDoItAll.Tests.Unit/CanDoItAll.Tests.Unit.csproj --filter FullyQualifiedName~ProcessDefinitionCatalogProjectionTests | Pass | proof/SB02/transcripts/process-canvas-version-contract-tests-after-final-edits.txt
dotnet test tests/CanDoItAll.Tests.Components/CanDoItAll.Tests.Components.csproj --filter FullyQualifiedName~ProcessWorkspaceShellTests | Pass | proof/SB03/transcripts/component-process-workspace-shell-after-final-edits.txt
dotnet test tests/CanDoItAll.Tests.Playwright/CanDoItAll.Tests.Playwright.csproj --filter FullyQualifiedName~ProcessShellSmokeTests.Process_shell_routes_render_global_and_project_scoped_workspaces | Pass | proof/SB04/transcripts/playwright-process-shell-final-navigation-smoke.txt
dotnet build CanDoItAll.slnx --no-restore | Pass | proof/SB06/transcripts/solution-build-after-final-edits-slnx.txt
python codex/skills/bundles/candoitall-bundle-preparation/scripts/validate_bundle.py codex/bundles/providers-processes-merge-readiness --profile initiative --stage completed --repo-root . | Pass | proof/SB06/transcripts/bundle-validator-completed-after-execution.txt
dotnet run --project src/CanDoItAll.Web/CanDoItAll.Web.csproj --no-build --urls http://127.0.0.1:5032 | Pass | proof/SB04/transcripts/web-5032-start.out.log